## Sheet1
Question | Answer | Source 1 (Page) | Source 1 (Content) | Source 2 (Page) | Source 2 (Content) | Source 3 (Page) | Source 3 (Content)
Earnest Money Deposit/Bid Security | The Earnest Money Deposit (EMD) or Bid Security is detailed in the NIT. It does not accrue interest. Unsuccessful bidders will have their EMD returned within 30 days of contract award. Successful bidders will receive their EMD upon providing Performance Security. The EMD may be forfeited if the successful bidder doesn't accept the Letter of Award (LOA) within 15 days, withdraws or alters their bid without consent before the bid validity period expires, revokes their tender after opening, increases quoted rates, or fails to commence work within the timeframe specified in the LOA/Contract (or within 15 days of award if not specified). The Bid Security will also be forfeited if the bidder withdraws or amends their tender, impairs or derogates from the tender, doesn't accept bid price corrections, or fails to sign the contract or provide performance security within the specified period. WAPCOS Limited reserves the right to forfeit the EMD for the successful bidder under certain conditions. The EMD can be submitted as a bank guarantee from an RBI-approved bank (as per Annexure-I). | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period.
What is the amount of the Earnest Money Deposit or Bid Security? | The provided text states that the Earnest Money Deposit (EMD) amount is equivalent to 5% of the contract price and can be submitted as a bank guarantee from an RBI-approved bank. The exact amount isn't specified because the contract price is not given. | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period.
What are the modes of Payment available for submission of the Earnest Money Deposit or Bid Security? | Based on the provided text, the Earnest Money Deposit (EMD) or Bid Security can be submitted as a Bank Guarantee issued by a Scheduled Commercial Bank approved by the Reserve Bank of India (RBI). The text also mentions a Demand Draft (DD) or "any other accepted instrument," but doesn't specify what other instruments are acceptable. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 12 | tender documents. The details of the DD/any other accepted instrument, physically sent, should tally with the details available in the scanned copy and the data entered during bid submission time. Otherwise the uploaded bid will be rejected. 7) Bidders are requested to note that they should necessarily submit their financial bids in the format provided and no other format is acceptable. If the price bid has been given as a standard BoQ format with the tender document, then the same is to be downloaded and to be filled by all the bidders. Bidders are required to download the BoQ file, open it and complete the white coloured (unprotected) cells with their respective financial quotes and other details (such as name of the bidder). No other cells should be changed. Once the details have been completed, the bidder should save it and submit it online, without changing the filename. If the BoQ file is found to be modified by the bidder, the bid will be rejected.
Is receipt of the Earnest Money Deposit or Bid Security required to be submmited with the Bid? | The provided text states that the Earnest Money Deposit (EMD) shall be as per the details mentioned in the NIT (Notice Inviting Tender). It does not explicitly state that it must be submitted *with* the bid, only that it is required. | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period.
What is the period of validity for Earnest Money Deposit or Bid Security? | The bids shall remain valid for acceptance for a period of 90 days from the date of opening of financial bids. In exceptional circumstances, the employer may request an extension before the original bid validity period expires. | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period. | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 16 | a prospective Bidder, modify the Bidding Documents by the issuance of a corrigendum/ addendum. No modification of Bid shall be permissible after last date of submission, whatever may be the reason. The Employer may at their discretion may extend the deadline for submission of Tender/ Bid, if considered necessary. Any corrigendum/ addendum thus issued shall be part of the bidding documents. Prospective Bidders shall download the same from the e-portal and submit along with the submission of Bid as token of acceptance 7.0 BID VALIDITY PERIOD Bids shall remain valid for acceptance for a period of 90 days (Ninety days) from the date of opening of financial Bids. In exceptional circumstances, prior to expiry of the original bid validity period, the Employer may request the Bidder for a specified extension in the period of validity. The request and the responses thereto shall be made in writing or by e-mail. A Bidder may
When will be the Earnest Money Deposit or Bid Security released? | The EMD/Bid Security of unsuccessful bidders will be returned within 30 days of the contract award. For successful bidders, it will be refunded upon receipt of the Performance Security. | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324
What are the Reasons for forfeiting of Earnest Money Deposit or Bid Security? | Based on the provided text, Earnest Money Deposit (EMD) or Bid Security may be forfeited for the following reasons: * **Lowest bidders refusing revised offers:** If all lowest bidders with the same quoted amount refuse to submit revised offers. 50% of each contractor's EMD will be forfeited. * **Revoking or amending a tender:** Withdrawing, amending, impairing, or derogating from a tender within its validity period. * **Not accepting bid price correction:** If a bidder does not accept the correction of their bid price during evaluation. * **Failure to sign contract or furnish performance security:** If the successful bidder fails to sign the contract or provide the required performance security within the specified timeframe. * **Non-commencement of work:** If the successful bidder does not commence work within the period stipulated in the Letter of Award/Contract (or within 15 days of award if not specified). * **Expiry of validity period:** If the validity period of the tender expires without written consent from the company. | Page 51 | those have quoted equal amount of their tenders. In case all the lowest contractors those have quoted same tendered amount, refuse to submit revised offers, then tenders are to be recalled after forfeiting 50% of EMD of each contractor. Contractor(s), whose earnest money is forfeited because of nonsubmission of revised offer, Page 51 of 324 | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period. | Page 44 | an accessory to such offences. Section 3 – Disqualification from tender process and exclusion from future contracts If the ‘Bidder/ Contractor’, before award or during execution, has committed a transgression through a violation of Section 2, above or in any other form such as to put their reliability or credibility in question, the Employer is entitled to disqualify the ‘Bidder/ Contractor’ from the tender process or take action as per the procedure mentioned in the “Guidelines on Banning of business dealings”. Section 4 – Compensation for Damages If the Employer has disqualified the ‘Bidder/ Contractor’ from the tender process prior to the award according to Section 3, the Employer is entitled to demand and recover from ‘Bidder/ Contractor’ the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to
Disqualification of bid | Based on the provided text, a bidder can be disqualified from the tender process for several reasons: * **Incorrect statements:** Making an incorrect statement regarding involvement in corrupt, fraudulent, collusive, or coercive practices. * **Violation of the Integrity Pact:** Not signing the Integrity Pact or violating its provisions. * **Transgressions affecting reliability or credibility:** Committing any transgression that questions the bidder's reliability or credibility, either before award or during execution. This includes violations of Section 2 (not fully detailed in this excerpt) or other actions. * **Corrupt, Fraudulent, Collusive, Or Coercive Practices:** Engaging in these practices, directly or through an agent, during the bidding process. In cases of disqualification before contract award, the employer may recover damages equivalent to the earnest money deposit or bid security. The employer may also take action as per the "Guidelines on Banning of business dealings," though the specifics of those guidelines aren't included in this text. | Page 13 | bidder recommended/ selected for award/awarded has, directly or through an agent, engaged in Corrupt, Fraudulent, Collusive, Or Coercive Practices incompeting for the Contract; Will sanction a party or its successors, including declaring ineligible, either indefinitely or for a stated period of time, to participate in any further Page 13 of 324 | Page 45 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If Bidder makes an incorrect statement on this subject, he can be disqualified from the tender process, or action can be taken as per the procedure mentioned in “Guidelines on Banning of business dealings”. Section 6 – Equal treatment of all Bidders/ Contractors/ Subcontractors In the case of Sub-contracting, the Principal Contractor shall take responsibility for the adoption of the Integrity Pact by the Sub-contractor. The Employer shall enter into agreements with identical conditions as this one with all Bidders and Contractors. The Employer shall disqualify from the tender process all bidders who do not sign this Pact or violate its provisions. Section 7 – Criminal charges against violating Bidder(s)/ Contractor(s)/ Subcontractor(s) If the Employer obtains knowledge of the conduct of a Bidder, Contractor or Subcontractor, or of an | Page 44 | an accessory to such offences. Section 3 – Disqualification from tender process and exclusion from future contracts If the ‘Bidder/ Contractor’, before award or during execution, has committed a transgression through a violation of Section 2, above or in any other form such as to put their reliability or credibility in question, the Employer is entitled to disqualify the ‘Bidder/ Contractor’ from the tender process or take action as per the procedure mentioned in the “Guidelines on Banning of business dealings”. Section 4 – Compensation for Damages If the Employer has disqualified the ‘Bidder/ Contractor’ from the tender process prior to the award according to Section 3, the Employer is entitled to demand and recover from ‘Bidder/ Contractor’ the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to
What are the reasons for disqualification of bid? | Based on the provided text, a bidder can be disqualified for the following reasons: * Making an incorrect statement regarding engaging in corrupt, fraudulent, collusive, or coercive practices. * Not signing the Integrity Pact or violating its provisions. * Committing a transgression that questions their reliability or credibility, either before award or during execution. This includes violations of Section 2 (not fully detailed in this excerpt) or other forms of misconduct. * If the bidder, directly or through an agent, engaged in corrupt, fraudulent, collusive, or coercive practices in competing for the contract. The employer is also entitled to demand compensation (Earnest Money Deposit/Bid Security) if a bidder is disqualified before the award. | Page 13 | bidder recommended/ selected for award/awarded has, directly or through an agent, engaged in Corrupt, Fraudulent, Collusive, Or Coercive Practices incompeting for the Contract; Will sanction a party or its successors, including declaring ineligible, either indefinitely or for a stated period of time, to participate in any further Page 13 of 324 | Page 45 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If Bidder makes an incorrect statement on this subject, he can be disqualified from the tender process, or action can be taken as per the procedure mentioned in “Guidelines on Banning of business dealings”. Section 6 – Equal treatment of all Bidders/ Contractors/ Subcontractors In the case of Sub-contracting, the Principal Contractor shall take responsibility for the adoption of the Integrity Pact by the Sub-contractor. The Employer shall enter into agreements with identical conditions as this one with all Bidders and Contractors. The Employer shall disqualify from the tender process all bidders who do not sign this Pact or violate its provisions. Section 7 – Criminal charges against violating Bidder(s)/ Contractor(s)/ Subcontractor(s) If the Employer obtains knowledge of the conduct of a Bidder, Contractor or Subcontractor, or of an | Page 44 | an accessory to such offences. Section 3 – Disqualification from tender process and exclusion from future contracts If the ‘Bidder/ Contractor’, before award or during execution, has committed a transgression through a violation of Section 2, above or in any other form such as to put their reliability or credibility in question, the Employer is entitled to disqualify the ‘Bidder/ Contractor’ from the tender process or take action as per the procedure mentioned in the “Guidelines on Banning of business dealings”. Section 4 – Compensation for Damages If the Employer has disqualified the ‘Bidder/ Contractor’ from the tender process prior to the award according to Section 3, the Employer is entitled to demand and recover from ‘Bidder/ Contractor’ the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to
How Authority will inform to bidder in case of disqualification of the bid? | I'm sorry, but this document does not explain how the Employer will inform a bidder of disqualification. | Page 16 | a prospective Bidder, modify the Bidding Documents by the issuance of a corrigendum/ addendum. No modification of Bid shall be permissible after last date of submission, whatever may be the reason. The Employer may at their discretion may extend the deadline for submission of Tender/ Bid, if considered necessary. Any corrigendum/ addendum thus issued shall be part of the bidding documents. Prospective Bidders shall download the same from the e-portal and submit along with the submission of Bid as token of acceptance 7.0 BID VALIDITY PERIOD Bids shall remain valid for acceptance for a period of 90 days (Ninety days) from the date of opening of financial Bids. In exceptional circumstances, prior to expiry of the original bid validity period, the Employer may request the Bidder for a specified extension in the period of validity. The request and the responses thereto shall be made in writing or by e-mail. A Bidder may | Page 18 | Employer via email mentioned in NIT, at least one working day prior to pre-bid meeting. The queries shall be discussed during the pre-bid meeting and the last date for submission of any further queries of Bidders shall be within two days from the date pre-bid meeting. Thereafter no further queries/clarifications shall be entertained. The Employer will reply to only those queries which received before the scheduled time as mentioned above via e- Page 18 of 324 | Page 19 | He should only submit bid if he considers himself eligible and he is in possession of all the documents required. The Technical Bid shall be uploaded with coloured scanned copies of following documents. All the documents must be Serial wise as stated below along with check list and clearly marked page no. on each page Format of Check List S.N Particular of Document Yes No Page Nos. (from – to) a) Authority to Sign the tender: a) In case of proprietary firm, the Proprietor shall sign with full name, current address OR by the authorized person holding Notarized Power of Attorney issued by the Proprietor for signing of this bid. b) In case of a Limited Company, Partnership firm or Corporation, the Application shall be signed by an authorized person holding the Power of Attorney. A certified copy of the Power of Attorney shall accompany the Application. Note: Power of Attorney duly notarized and on a stamp paper of appropriate value, issued and
What are the impacts in case of disqualification from bidding process? | Based on the provided text, if a bidder is disqualified from the tender process before the award, the employer can demand and recover the damages equivalent to the Earnest Money Deposit/Bid Security. If the contract is terminated due to disqualification, further consequences may apply, although the specifics aren't detailed in this excerpt. Additionally, disqualification may lead to being declared ineligible to participate in future bids, either indefinitely or for a specified period, as per the "Guidelines on Banning of business dealings". | Page 44 | an accessory to such offences. Section 3 – Disqualification from tender process and exclusion from future contracts If the ‘Bidder/ Contractor’, before award or during execution, has committed a transgression through a violation of Section 2, above or in any other form such as to put their reliability or credibility in question, the Employer is entitled to disqualify the ‘Bidder/ Contractor’ from the tender process or take action as per the procedure mentioned in the “Guidelines on Banning of business dealings”. Section 4 – Compensation for Damages If the Employer has disqualified the ‘Bidder/ Contractor’ from the tender process prior to the award according to Section 3, the Employer is entitled to demand and recover from ‘Bidder/ Contractor’ the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to | Page 13 | bidder recommended/ selected for award/awarded has, directly or through an agent, engaged in Corrupt, Fraudulent, Collusive, Or Coercive Practices incompeting for the Contract; Will sanction a party or its successors, including declaring ineligible, either indefinitely or for a stated period of time, to participate in any further Page 13 of 324 | Page 45 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If Bidder makes an incorrect statement on this subject, he can be disqualified from the tender process, or action can be taken as per the procedure mentioned in “Guidelines on Banning of business dealings”. Section 6 – Equal treatment of all Bidders/ Contractors/ Subcontractors In the case of Sub-contracting, the Principal Contractor shall take responsibility for the adoption of the Integrity Pact by the Sub-contractor. The Employer shall enter into agreements with identical conditions as this one with all Bidders and Contractors. The Employer shall disqualify from the tender process all bidders who do not sign this Pact or violate its provisions. Section 7 – Criminal charges against violating Bidder(s)/ Contractor(s)/ Subcontractor(s) If the Employer obtains knowledge of the conduct of a Bidder, Contractor or Subcontractor, or of an
Performance Security | Based on the provided text, Performance Security is a guarantee, likely in the form of a bank guarantee or deposit receipt from a scheduled commercial bank approved by the Reserve Bank of India (RBI), that ensures the contractor fulfills their contractual obligations. It's valid until the successful completion of the Defect Liability Period (DLP), typically one year after project completion. Failure to provide or comply with the requirements for Performance Security can lead to contract cancellation. The Performance Security is returned to the contractor without interest after the DLP is completed. Delays in procuring the Performance Security may be addressed by requesting an extension from the competent authority. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
What is the amount of the Performance Security required to be submitted? | The provided text mentions a 5% security deposit of the tendered value, but it does not specify the tendered value itself. Therefore, the exact amount of the Performance Security cannot be determined. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
What is the percentage of Contract Value required to be submitted as the Performance Security? | The provided text does not specify a percentage of the contract value required for the performance security. It mentions a 5% security deposit (Clause 1A), but this is a separate item from the performance security. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
What are the modes of Payment available for submission of the Performance Security? | Based on the provided text, the Performance Security can be submitted as a deposit receipt from a Scheduled Commercial Bank approved by the Reserve Bank of India (RBI), payable at Delhi/Gurgaon in favor of WAPCOS Limited. A bank guarantee is also acceptable, with confirmation sought through the Structured Financial Messaging System (SFMS). | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
What is the time period for the submission of the Performance Security? | The provided text states that the period for submission of the Performance Security can be extended by the competent authority upon written request from the bidder, stating the reasons for any delays. There is no specific initial time period given. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
What is the period of validity for Performance Security? | The Performance Security is initially valid up to the stipulated date of completion plus a one-year claim period beyond the completion of all contractual obligations, including the Defect Liability Period (DLP). If the completion time is extended, the validity of the Performance Security will also be extended. It will be returned to the contractor without interest after the completion of the DLP, no later than 365 days after. | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
When will be the Performance Security released? | The Performance Security will be released after the successful completion of the Defect Liability Period. One document states this will be after one year, while another says it will be no later than 365 days after completion of the Defect Liability Period. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
What are the Reasons for forfeiting of Performance Security? | Based on the provided text, the only reason for forfeiting the performance security is the failure of the successful bidder to comply with the requirements of the performance security. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
Is the format for Bank Guarantee against Performance Security provided in the document? | No, the document does not provide a specific format for a Bank Guarantee against Performance Security. It mentions acceptable forms of Performance Security (Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt, or Bank Guarantee from a Commercial Bank), but doesn't include a sample Bank Guarantee format. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 57 | Contract on written request of the contractor stating the reason for delays in procuring the Performance Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks. In case a fixed deposit receipt of any Bank is furnished by the contractor to the Government as part of the Page 57 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
What is the provision for encashment of the Bank Guarantee against Performance Security? | The provided text states that if a fixed deposit receipt is used as performance guarantee and the bank cannot make payment, the contractor is responsible for the loss and must provide additional security. There is no information about the encashment process for a Bank Guarantee specifically. | Page 57 | Contract on written request of the contractor stating the reason for delays in procuring the Performance Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks. In case a fixed deposit receipt of any Bank is furnished by the contractor to the Government as part of the Page 57 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
What is the provision in case of delayed submission of the Performance Security? | The competent authority can extend the period for submission of the Performance Security upon written request from the bidder, stating the reasons for the delay. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the
What is the provision in case of Non-submission of the Performance Security? | The provided text states that failure of the successful bidder to comply with the requirements of performance security constitutes sufficient grounds for cancellation of the award. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
Additional Security Deposit | Based on the provided text, there is mention of a Security Deposit that will be released after approval by SMFPL. There is no information about an *additional* security deposit. | Page 156 | principal and his successors against all loss, damage, cost expense otherwise which may be incurred by him by reason of any default on the part of the GUARANTOR in performance and observance of this Supplementary Agreement. As to the amount of loss and/or damage and/or cost incurred by the Principal Employer the decision of the owner will be final and binding on the parties. IN WITHNES WHEREOF those presents have been executed by the GUARANTOR ………………………..(Name and Designation who sign the Contract) on behalf of Page 156 of 324 | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered
Is there a provision for submission of Additional Security Deposit? | The provided text mentions a security deposit and its release conditions, but it does not contain any information about an additional security deposit. Therefore, I don't know. | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered
What is the formula given to calculate the Additional Security Deposit? | The provided text does not contain a formula for calculating an additional security deposit. It mentions security deposits being released after approval and withheld in cases of contractor default, but no formula is given. | Page 156 | principal and his successors against all loss, damage, cost expense otherwise which may be incurred by him by reason of any default on the part of the GUARANTOR in performance and observance of this Supplementary Agreement. As to the amount of loss and/or damage and/or cost incurred by the Principal Employer the decision of the owner will be final and binding on the parties. IN WITHNES WHEREOF those presents have been executed by the GUARANTOR ………………………..(Name and Designation who sign the Contract) on behalf of Page 156 of 324 | Page 95 | to withhold and also have a lien to retain such sum or sums in whole or in part from the security, if any deposited by the contractor and for the purpose aforesaid, the Engineer-in-charge or the Government shall be entitled to withhold the security deposit, if any, furnished as the case may be and also have a lien over the same pending finalization or adjudication of any such claim. In the event of the security being insufficient to cover the claimed amount or amounts or if no security has been taken from the contractor, the Engineer-in-Charge or the Government shall be entitled to withhold and have a lien to retain to the extent of such claimed amount or amounts referred to above, from any sum or sums found payable or which may at any time thereafter become payable to the contractor under the same contract or any other Page 95 of 324 | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of
What is the amount of the Additional Security Deposit required to be submitted? | The provided text mentions a Security Deposit equal to 5% of the tendered amount, but it does not specify an additional security deposit amount. | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 53 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 should be written before the figure of rupees and word ‘P’ after the decimal figures, e.g. ‘Rs. 2.15P and in case of words, the word ‘Rupees’ should precede and the word ‘Paisa’ should be written at the end 11. i. The Contractor whose tender is accepted, will be required to furnish performance guarantee at specified percentage of the tendered amount as mentioned in NIT and within the period specified in SCC. This guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee of any Commercial Bank. ii. The contractor whose tender is accepted will also be required to furnish by way of Security Deposit for the fulfillment of his contract, an amount equal to 5% of the tendered amount of the work. The Security deposit will be collected by deductions from the running bills as well as final bill of the contractor at the rates | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered
What are the modes of Payment available for submission of the Additional Security Deposit? | The provided text states that the additional security deposit (Performance Security) can be submitted in two ways: 1. A Bank Guarantee issued by a Scheduled Commercial Bank approved by the Reserve Bank of India (RBI). 2. A deposit receipt from a Scheduled Commercial Bank approved by the RBI, payable to WAPCOS Limited in Delhi/Gurgaon. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 15 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 2.0 EARNEST MONEY DEPOSIT (EMD) / BID SECURITY The Earnest Money Deposit shall be as per the details mentioned in NIT. EMD shall not carry any interest. The Bid Security/ EMD of the unsuccessful bidder shall be returned at the earliest after expiry of final bid validity period and latest by 30 th days after the award of the contract. Bid Security shall be refunded to the successful bidder on receipt of Performance Security. The successful bidder shall accept the Letter of Award (LOA) within 15 (Fifteen) days from receipt of the same, failing which the EMD shall be forfeited and the award of work may be liable to be cancelled. If any bidder withdraws or make any changes in his offer already submitted before the expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder.
What is the time period for the submission of the Additional Security Deposit? | The provided text does not specify a time period for the submission of an additional security deposit. It only states that if the performance guarantee is not met, the contractor shall "forthwith on demand furnish additional security". | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC. | Page 119 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added  a deposit receipt of a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) in favour of WAPCOS Limited payable at Delhi/ Gurgaon. b) The confirmation of the Bank Guarantee shall be sought from the issuing bank through Structured Financial Messaging System (SFMS), from our banker Indian Overseas Bank, NHB, Gurgram, Branch Code: 1935, IFSC code: IOBA0001935 a nd Beneficiary as WAPCOS Limited. This shall also be applicable in respect of confirmation of any extension of the Bank Guarantee as and when required. c) The period for submission of the Performance Security can be extended by the competent authority upon written request received from the Bidder stating the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.
What is the period of validity for Additional Security Deposit? | The provided text does not specify a period of validity for an Additional Security Deposit. It mentions that a contractor may be required to furnish additional security to make good a deficit, but doesn't state how long that additional security must remain in place. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324
When will be the Additional Security Deposit released? | The provided text describes the release of the *security deposit*, not an additional security deposit. Fifty percent will be released after 18 months from completion or when the final bill is passed (whichever is later). The remaining 50% is released after the defect liability period, provided satisfactory performance and after deduction of government dues. There is mention of replacing the retention amount with a bank guarantee, but no information about an additional security deposit. | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC. | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest
What are the Reasons for forfeiting of Additional Security Deposit? | The provided text does not contain information about forfeiting an Additional Security Deposit. It describes reasons for forfeiting an Earnest Money Deposit (EMD) and Bid Security, and it mentions a Performance Security and Security Deposit, but not an Additional Security Deposit and the reasons for its forfeiture. | Page 15 | expiry of the validity period or any extension thereof without the written consent of the company, the EMD amount will be forfeited for such act of the bidder. WAPCOS Limited reserves the right of forfeiture of Earnest Money deposit (EMD) in case of the successful bidder. i. After opening of Tender, revokes his tender within the validity period or increases his earlier quoted rates. ii. Does not commence the work within the period as per LOA/Contract. In case the LOA/Contract is silent in this regard then within 15 days after award of contract. The Bid Security will be forfeited in the bidder i) withdraws or amends its/ his tender; ii) impairs or derogates from the tender in any respect within the period of validity of the tender; iii) If the bidder does not accept the correction of his bid price during evaluation; and iv) If the successful bidder fails to sign the contract or furnish the required performance security within the specified period. | Page 51 | those have quoted equal amount of their tenders. In case all the lowest contractors those have quoted same tendered amount, refuse to submit revised offers, then tenders are to be recalled after forfeiting 50% of EMD of each contractor. Contractor(s), whose earnest money is forfeited because of nonsubmission of revised offer, Page 51 of 324 | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324
Is the format for Bank Guarantee against Additional Security Deposit provided in the document? | The provided text mentions several types of bank guarantees (performance, mobilization advance payment, EMD, etc.), but it does not explicitly state whether a format for a bank guarantee against an additional security deposit is included. | Page 118 | forms given below for an amount equivalent to 5% of the Contract price:  a Bank Guarantee issued by a Scheduled Commercial Bank approved by Reserve Bank of India (RBI) as per Annexure-I of Bid document; or Page 118 of 324 | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered | Page 139 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 SECTION – VI ANNEXURES ANNEXURE – I FORMAT FOR CONTRACT AGREEMENT AND LETTER OF AWARD ANNEXURE – II FORMAT FOR PERFORMANCE BANK GUARANTEE ANNEXURE – III FORMAT FOR MOBILIZATION ADVANCE PAYMENT BANK GUARANTEE ANNEXURE – IV FORMAT FOR INDENTURE FOR SECURED ADVANCES ANNEXURE – V FORMAT OF BANK GUARANTEE FOR EMD ANNEXURE – VI FORMAT FOR SEEKING EXTENSION OF TIME ANNEXURE – VII FORMAT OF GUARANTEE BOND /AFFIDAVIT FOR WORKS ANNEXURE – VIII CONTRACT FOR REMOVAL OF DEFECTS AFTER COMPLETION IN RESPECT OF WATER PROOFING WORKS ANNEXURE – IX FORMAT FOR GUARANTE BONDS FOR ANTI -TERMITE TREATMENT ANNEXURE – X SAFETY CODES ANNEXURE – XI MODEL RULES FOR THE PROTECTION OF HEALTH AND SANITARY ARRANGEMENTS FOR WORKERS EMPLOYED BY CONTRACTORS ANNEXURE – XII CONTRACTOR’S LABOUR REGULATIONS ANNEXURE – XIII STANDARD FORMAT OF SBLC Page 139 of 324
What is the provision for encashment of the Bank Guarantee against Additional Security Deposit? | I'm sorry, but this question cannot be answered from the given context. The provided text mentions bank guarantees and security deposits in relation to contract performance and potential contractor delays, but it does not detail the specific provision for encashment of a bank guarantee against an additional security deposit. | Page 57 | Contract on written request of the contractor stating the reason for delays in procuring the Performance Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks. In case a fixed deposit receipt of any Bank is furnished by the contractor to the Government as part of the Page 57 of 324 | Page 95 | to withhold and also have a lien to retain such sum or sums in whole or in part from the security, if any deposited by the contractor and for the purpose aforesaid, the Engineer-in-charge or the Government shall be entitled to withhold the security deposit, if any, furnished as the case may be and also have a lien over the same pending finalization or adjudication of any such claim. In the event of the security being insufficient to cover the claimed amount or amounts or if no security has been taken from the contractor, the Engineer-in-Charge or the Government shall be entitled to withhold and have a lien to retain to the extent of such claimed amount or amounts referred to above, from any sum or sums found payable or which may at any time thereafter become payable to the contractor under the same contract or any other Page 95 of 324 | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered
What is the provision in case of delayed submission of the Additional Security Deposit? | The provided text does not specify a provision for delayed submission of an additional security deposit. It mentions consequences for failure to provide performance security (clauses 18d and 18e), and it describes the release of the security deposit (clause 17.6 and Clause 1A), but it does not address delays in *additional* security deposit submissions. | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 95 | to withhold and also have a lien to retain such sum or sums in whole or in part from the security, if any deposited by the contractor and for the purpose aforesaid, the Engineer-in-charge or the Government shall be entitled to withhold the security deposit, if any, furnished as the case may be and also have a lien over the same pending finalization or adjudication of any such claim. In the event of the security being insufficient to cover the claimed amount or amounts or if no security has been taken from the contractor, the Engineer-in-Charge or the Government shall be entitled to withhold and have a lien to retain to the extent of such claimed amount or amounts referred to above, from any sum or sums found payable or which may at any time thereafter become payable to the contractor under the same contract or any other Page 95 of 324
What is the provision in case of Non-submission of the Additional Security Deposit? | I'm sorry, but this document does not contain information about the provision in case of non-submission of the additional security deposit. | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC. | Page 95 | to withhold and also have a lien to retain such sum or sums in whole or in part from the security, if any deposited by the contractor and for the purpose aforesaid, the Engineer-in-charge or the Government shall be entitled to withhold the security deposit, if any, furnished as the case may be and also have a lien over the same pending finalization or adjudication of any such claim. In the event of the security being insufficient to cover the claimed amount or amounts or if no security has been taken from the contractor, the Engineer-in-Charge or the Government shall be entitled to withhold and have a lien to retain to the extent of such claimed amount or amounts referred to above, from any sum or sums found payable or which may at any time thereafter become payable to the contractor under the same contract or any other Page 95 of 324 | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324
Retention Money | Based on the provided text, retention money is a sum deducted from payments to the contractor (5% from each running and final bill, excluding GST). The contractor can replace this retention amount with an unconditional bank guarantee (BG) once the retention amount reaches half its maximum limit, and again when it reaches the full maximum limit. Half of the retention money (or its BG equivalent) is released upon issuance of the taking-over certificate (TOC), with proportional releases if TOCs are issued in parts. The other half is released 365 days after the Defect Liability Period (DLP) of the works or final payment, whichever is earlier, upon engineer certification. If different sections have different DLPs, the latest DLP applies. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 96 | claim of the Engineer- in-charge or Government or such other person or persons in respect of payment of a sum of money arising out of or under any other contract made by the contractor with the Engineer- in-charge or the Government or with such other person or persons. It is an agreed term of the contract that the sum of money so withheld or retained under this clause by the Engineer- in-charge or the Government will be kept withheld or retained as such by the Engineer-in-charge or the Government or till his claim arising out of the same contract or any other contract is either mutually settled or determined by the arbitration clause or by the competent court, as the case may be and that the contractor shall have no claim for interest or damages whatsoever on this account or on any other ground in respect of any sum of money withheld or retained under this clause and duly notified as such to the contractor Page 96 of 324
What is the Preovision for the deduction of the Retention Money provided? | The contractor may have a retention amount deducted at a rate of 5% from each running and final bill, excluding GST. The contractor can replace this retention amount with an unconditional bank guarantee (BG) once the amount reaches half the value of the retention money limit, or once it reaches the maximum limit. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 96 | claim of the Engineer- in-charge or Government or such other person or persons in respect of payment of a sum of money arising out of or under any other contract made by the contractor with the Engineer- in-charge or the Government or with such other person or persons. It is an agreed term of the contract that the sum of money so withheld or retained under this clause by the Engineer- in-charge or the Government will be kept withheld or retained as such by the Engineer-in-charge or the Government or till his claim arising out of the same contract or any other contract is either mutually settled or determined by the arbitration clause or by the competent court, as the case may be and that the contractor shall have no claim for interest or damages whatsoever on this account or on any other ground in respect of any sum of money withheld or retained under this clause and duly notified as such to the contractor Page 96 of 324 | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and
What is the maximum limit of the retention money amount? | I'm sorry, but the provided text does not specify the maximum limit of the retention money amount. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 96 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 contract with the Engineer- in-Charge or with the Government or any contracting person through the Engineer-in-Charge pending finalization of adjudication of any such claim. It is an agreed term of the contract that the sum of money or moneys so withheld or retained under the lien referred to above by the Engineer- in-Charge or Government will be kept withheld or retained as such by the Engineer- in-Charge or Government till the claim arising out of or under the contract is determined by the arbitrator (if the contract is governed by the arbitration clause) by the competent court, as the case may be and that the contractor will have no claim for interest or damages whatsoever on any account in respect of such withholding or retention under the lien referred to above and duly notified as such to the contractor. For the purpose of this clause, where the contractor is a partnership firm or a limited
When will be the Retention Money released? | Half of the retention money (or bank guarantee replacing it) is released upon issuance of the taking-over certificate. If the certificates are issued in parts, the release is proportional to the value of each part, as determined by the engineer. The other half is released 365 days after the Defect Liability Period (DLP) of the works or final payment, whichever comes first, upon engineer certification. If different sections have different DLPs, the latest DLP expiration date applies. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of
what are the provisions for the release of the retention money? | Half of the retention money (or bank guarantee replacing it) is released upon issuance of the taking-over certificate. If the certificates are issued in parts, the release is proportional to the value of each part, as determined by the engineer. The other half is released 365 days after the Defect Liability Period (DLP) of the works or final payment, whichever is earlier, upon engineer certification. If different sections have different DLPs, the latest DLP expiration date applies. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 80 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 17.3 within specified time limit, the Engineer- in-Charge may also initiate legal and/or other actions under other applicable laws in addition to other remedies available in the contract. 17.6 Release of security deposit Fifty percent (50%) of the security deposit of the contractor shall be retained for a period of 18 (eighteen) months from the date of completion of work as per completion certificate issued by the Engineer-in-Charge or till the final bill has been passed whichever is later. This balance fifty percent (50%) security deposit shall be released after completion of defect liability period. Provided further, that the security deposit shall be released within a month of its due date as stated above only if satisfactory performance is observed during the said period and after deduction of Government dues from the contractor, if any. CLAUSE 18 : CONTRACTOR SUPPLY TOOLS & PLANTS ETC.
What are the Reasons for forfeiting of Retention Money? | Based on the provided text, there is no information about reasons for forfeiting retention money. The text only describes how the retention money can be replaced with a bank guarantee and how it is released. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 51 | those have quoted equal amount of their tenders. In case all the lowest contractors those have quoted same tendered amount, refuse to submit revised offers, then tenders are to be recalled after forfeiting 50% of EMD of each contractor. Contractor(s), whose earnest money is forfeited because of nonsubmission of revised offer, Page 51 of 324 | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and
What is the provision of Bank Guarantee against release of retention money? | The contractor can replace the retention amount with an unconditional Bank Guarantee (BG) after the retention amount reaches half its maximum limit, and again after it reaches the maximum limit. Half the retention money (or its BG equivalent) is released upon issuance of the Taking-Over Certificate (or in proportion to partial TOCs). The other half is released 365 days after the Defect Liability Period (DLP) of the works or final payment, whichever is earlier, upon engineer certification. If different sections have different DLPs, the latest DLP expiration date applies. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 158 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 ANNEXURE VIII (a) FORM OF BANK GUARANTEE BOND FOR WATER PROOFING WORK (Not required for the works of Tendered Value below Rs. 5.0 Crore excluding GST) 1. In considerable of the ……………………………………………….(Name of Principal Employer) (hereinafter called “The Owner”) having agreed to exempt.......................................... (Hereinafter called the said contractor(s)) from the demand, under the terms and conditions of the Agreement No............................... dated...................................Made between .................. and ......................... For the work of....................................... (hereinafter called “The said Agreement”) security deposit for the due fulfillment by the said contractor(s) of the terms & conditions contained in the said Agreements for the work of Anti water proofing work on production of an irrevocable Bank Guarantee for Rs. (……………………@0.5% of the Tendered
What are the provisions regarding retention money are there in case of termination? | The provided text doesn't specify what happens to retention money in case of contract termination. It only states that if the contract is terminated or rescinded, the performance guarantee is forfeited. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 58 | 30 days of the service of notice to this effect by Engineer in-Charge. i. In the event of the contract being determined or rescinded under provision of any of the Clause/Condition of the agreement, the performance guarantee shall stand forfeited in full and shall be absolutely at the disposal of the WAPCOS. ii. The performance Guarantee shall be refunded to the contractor after recording successful Completion of Defect Liability Period. CLAUSE 1A: RECOVERY OF SECURITY DEPOSIT The Bidder whose tender(s) may be accepted shall permit WAPCOS at the time of making any payment to Contractor for work done under the contract to deduct a sum at the rate of 5% from each running and final bill excluding GST. The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and | Page 146 | bank shall not be released of its obligations under these presents by any exercise by the Employer of its liberty with reference to the matters aforesaid or any of them or by reason of any other act or forbearance or other acts of omission or commission on the part of the Employer or any other indulgence shown by the Employer or by any other matter or thing whatsoever which under law would but for this provision, have the effect of relieving the Bank. Page 146 of 324
Mobilization Advance or Advance Payment | Based on the provided text, there are two types of advances: * **Secured Advance on Non-Perishable Materials:** This is 75% of the assessed value of the materials and is recovered as the materials are used. * **Mobilization Advance:** This is up to 10% of the tendered value and requires a Standby Letter of Credit (SBLC). It may be paid in installments, with subsequent installments contingent upon satisfactory utilization of prior installments as determined by the Engineer-in-Charge. | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 71 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 This advance shall further be subject to the condition that such plant and equipment (a) are considered by the Engineer-in-Charge to be necessary for the works; (b) and are in working order and are maintained in working order; (c) hypothecated to the WAPCOS as specified by the Engineer-in-Charge before the payment of advance is released. The contractor shall not be permitted to remove from the site such hypothecated plant and equipment without the prior written permission of the Engineer- in-Charge. The contractor shall be responsible for maintaining such plant and equipment in good working order during the entire period of hypothecation failing which such advance shall be entirely recovered in lump sum. For this purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and | Page 70 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Engineer-in-Charge shall be final and binding on the contractor in this matter. No secured advance, shall however, be paid on high-risk materials such as ordinary glass, sand, petrol, diesel etc. (ii) MOBILISATION ADVANCE Mobilization advance not exceeding 10% of the tendered value may be given, if requested by the contractor in writing within one month of the order to commence the work. Such advance shall be in two or more installments to be determined by the Engineer- in- Charge at his sole discretion. The first installment of such advance shall be released by the Engineer- in-charge to the contractor on a request made by the contractor to the Engineer- in-Charge in this behalf. The second and subsequent installments shall be released by the Engineer- in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge.
Is there a Provision for Mobilization Advance or Advance Payment? | Yes, there is a provision for a mobilization advance (Clause 10 B(ii)). It's 10% of the tendered value, paid in two installments, requiring a Standby Letter of Credit (SBLC). There is also mention of a secured advance on non-perishable materials (Clause 10 B(i)). | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What is the Percentage of Contract Value mentioned for the mobilization advance or Advance Payment? | The mobilization advance is 10% of the tendered value. This is paid in two installments: 5% upon commencement of work, and another 5% after 10% of the contract price is achieved. | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
How many installments are there for the mobilization advance or Advance Payment? | The mobilization advance is paid in two installments. | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
What are the provisions for the receipt of the mobilization advance or Advance Payment? | Based on the provided text, the mobilization advance is 10% of the tendered value, payable upon submission of a Standby Letter of Credit (SBLC) from a Nationalized/Scheduled commercial bank for 110% of the advance amount, valid for the contract period. The interest rate and calculation are based on the SBI Lending Rate (MCLR) and other SBI provisions for the Real Estate sector. Above 10%, the advance is paid in two installments: 5% at the commencement of work and 5% after achieving 10% financial progress. All payments are released via e-transfer through RTGS in India directly to the contractor's bank account. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What is the start date of the recovery of the mobilization advance or Advance Payment? | The recovery of the mobilization advance begins after the first 10% of the gross value of the work is executed and paid. | Page 121 | date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of Page 121 of 324 | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What is the time period in which mobilization advance or Advance Payment will be recovered? | The mobilization advance will be recovered by deduction from the contractor's bills. This begins after the first 10% of the gross value of the work is executed and paid. Recovery continues on a pro-rata basis until the advance is fully recovered by the time 80% of the gross value of the work is completed. | Page 121 | date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of Page 121 of 324 | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What are the Provisions for Bank Guarantee or letter of credit against Mobilization Advance or Advance Payment? | For Mobilization Advance, a Standby Letter of Credit (SBLC) from a Nationalized/Scheduled commercial bank is required for 110% of the advance amount, valid for the contract period. For other advances, a Bank Guarantee from a Scheduled Commercial Bank is required for 110% of the advance amount and must be renewed to cover the balance amount and likely period of complete recovery. | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
what is the validity of Bank Guarantee or letter of credit provided against mobilization advance or Advance Payment? | The provided text states that the bank guarantee for the mobilization advance must be valid for the contract period and be renewed from time to time to cover the balance amount and likely period of complete recovery. The exact validity period of the Letter of Credit itself is not specified, but the claim period is 12 months from the expiry date of the Letter of Credit. | Page 177 | the date of expiry for submission of documents for negotiation to the bank. 2. We are liable to pay upto the guaranteed amount only and only if we receive from you a written claim or demand within the claim period not later than 12 months from the said expiry date relating to default that happened during the guarantee period and shall your rights under this Letter of Credit (L/C) shall be extinguished and our liability under the Letter of Credit (L/C) shall stand discharged unless such written claim or demand is received by us from you on or before ________ being the date of expiry of the claim period. (Indicate a date one year after validity of Letter of Credit). 3. This Letter of Credit covers payment towards Mobilization Advance as a part of the agreement. 4. All bank charges including negotiation / handling and interest charges will be borne by the opener of Letter of Credit i.e. (Name of the Contractor). | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 159 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 to the said agreement and we shall not be relieved from our liability by reason of any such variation, or extension being granted to the said contractors(s) or for any bearance, act of commission of the part of Principal Employer or any indulgence by Principal Employer to the said contractor(s) or by any such matter of thing whatsoever which under the law relating to sureties would, but for this provision, have effect of so relieving us. 6. This guarantee will not be discharged due to the change in the constitution of Bank or the contractor(s). 7. We……………………… (indicate the name of the Bank) lastly undertake not to revoke this guarantee except with the previous consent of Principal Employer in writing 8. This guarantee shall be valid upto ........................... unless extended on demand by Principal Employer. Notwithstanding anything mentioned above, our liability against this guarantee is
is mobilization advance or Advance Payment interest bearing or interest free? | The provided text states that mobilization advance is interest-bearing. The interest rate and calculation method are based on the State Bank of India's (SBI) Lending Rate (MCLR) and other SBI provisions for the Real Estate sector. | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in
What is the applicable percenatge of interest on the mobilization advance or Advance Payment? | The provided text gives conflicting information regarding the interest rate on mobilization advances. One section states the interest rate is 10% per annum, while another says it's based on the State Bank of India's (SBI) Lending Rate (MCLR) and other SBI provisions for the Real Estate sector. | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in
Material Advance | Based on the provided text, a material advance is a payment made to the contractor for materials brought to the site that are non-perishable, non-fragile, and non-combustible, and are in accordance with the contract. These materials must be adequately stored and protected. Once these materials are incorporated into the work, the advance is deducted from the next payment. Advances can also be made for perishable, fragile, and combustible materials with the Engineer-in-Charge's approval and comprehensive insurance coverage. The contractor must own the materials outright and they cannot be used for anything other than the project. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 148 | aforesaid shall be employed by the Contractor in or towards expediting the execution of the said works and for no other purpose whatsoever. (2) That the materials detailed in the said Account of Secured Advances which have been offered to and accepted by the WAPCOS as security are absolutely the Contractor’s own property and free from encumbrances of any kind and the contractor will not make any application for or receive a further advance on the security of materials which are not absolutely his own property and free from encumbrances of any kind and the Contractor indemnifies the WAPCOS against all claims to any materials in respect of which an advance has been made to him as aforesaid. (3) That the materials detailed in the said Account of Secured Advances and all other materials on the security of which any further advance or advances may hereafter be made as aforesaid (hereinafter called the said materials) shall be used by the Contractor solely in the execution of the | Page 211 | worksites. In the present day context, it has become essential to adopt “Use of Innovative Technologies and Materials in Construction ” for faster, ecofriendly and quality construction. Speed, quality, environmental issues and durability are considered to be governing the construction process due to large requirement of housing. Construction technologies which perform better in speed of construction, quality and durability will last longer and others may not. Though large numbers of construction technologies are available with different names, but most of them are with slight innovation or usi ng some component or application used in material or construction methodology and RCC and steel still remain main construction materials The constant rising costs of building materials and the declining quality of housing and building construction are cau sing concern to Central & State Governments. It is now
Is there a Provision for Material Advance? | Yes, there is a provision for material advance. The provided text details conditions for advances on non-perishable, non-fragile, and non-combustible materials, as well as for perishable, fragile, and combustible materials (with insurance and Engineer-in-Charge approval). | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and
What is the Percentage of Contract Value mentioned for the Material Advance? | The provided text states that a secured advance of 75% of the assessed value of non-perishable, non-fragile, and non-combustible materials is available. There is no percentage of the *contract value* mentioned for material advances. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and
How many installments are there for the Material Advance? | The provided text doesn't specify the number of installments for the material advance. It only states that when materials are incorporated into the work, the advance is deducted from the next payment. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 148 | aforesaid shall be employed by the Contractor in or towards expediting the execution of the said works and for no other purpose whatsoever. (2) That the materials detailed in the said Account of Secured Advances which have been offered to and accepted by the WAPCOS as security are absolutely the Contractor’s own property and free from encumbrances of any kind and the contractor will not make any application for or receive a further advance on the security of materials which are not absolutely his own property and free from encumbrances of any kind and the Contractor indemnifies the WAPCOS against all claims to any materials in respect of which an advance has been made to him as aforesaid. (3) That the materials detailed in the said Account of Secured Advances and all other materials on the security of which any further advance or advances may hereafter be made as aforesaid (hereinafter called the said materials) shall be used by the Contractor solely in the execution of the
What are the provisions for the receipt of the Material Advance? | Based on the provided text, to receive a material advance, the materials must be non-perishable, non-fragile, and non-combustible. They must also comply with the contract, be stored properly to prevent damage, and not yet be incorporated into the work. The advance is recovered from subsequent payments. For perishable, fragile, or combustible materials, an advance is possible with the Engineer-in-Charge's approval and comprehensive insurance provided by the contractor. Before any advance is released, the contractor must provide a bank guarantee for 110% of the advance amount, valid for the contract period and renewed as needed. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
What is the start date of the recovery of the Material Advance? | The provided text states that recovery of the material advance begins after the first 10% of the gross value of the work has been completed. It does not specify a date, only a percentage of completion. | Page 121 | date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of Page 121 of 324 | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What is the time period in which Material Advance will be recovered? | The provided text states that when materials are incorporated into the work, the material advance is recovered/deducted from the next payment. There's no specific time period given for this. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What are the Provisions for Bank Guarantee or letter of credit against Material Advance? | Before any installment of advance is released, the contractor must provide a Bank Guarantee from a scheduled commercial bank for 110% of the advance amount, valid for the contract period. This guarantee must be renewed to cover the remaining balance and likely period of complete recovery. | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 57 | Contract on written request of the contractor stating the reason for delays in procuring the Performance Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks. In case a fixed deposit receipt of any Bank is furnished by the contractor to the Government as part of the Page 57 of 324 | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324
what is the validity of Bank Guarantee or letter of credit provided against Material Advance? | The provided text states that the Bank Guarantee for the advance must be valid for the contract period and renewed to cover the balance amount and likely period of complete recovery. There is no specific validity period mentioned for a Letter of Credit provided against a material advance, only that claims must be made within 12 months of the expiry date of the Letter of Credit. | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 177 | the date of expiry for submission of documents for negotiation to the bank. 2. We are liable to pay upto the guaranteed amount only and only if we receive from you a written claim or demand within the claim period not later than 12 months from the said expiry date relating to default that happened during the guarantee period and shall your rights under this Letter of Credit (L/C) shall be extinguished and our liability under the Letter of Credit (L/C) shall stand discharged unless such written claim or demand is received by us from you on or before ________ being the date of expiry of the claim period. (Indicate a date one year after validity of Letter of Credit). 3. This Letter of Credit covers payment towards Mobilization Advance as a part of the agreement. 4. All bank charges including negotiation / handling and interest charges will be borne by the opener of Letter of Credit i.e. (Name of the Contractor). | Page 57 | Contract on written request of the contractor stating the reason for delays in procuring the Performance Guarantee, to the satisfaction of the Engineer-in-Charge. This Guarantee shall be in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt or Bank Guarantee from any of the Commercial Banks. In case a fixed deposit receipt of any Bank is furnished by the contractor to the Government as part of the Page 57 of 324
is Material Advance interest bearing or interest free? | The provided text states that the mobilization advance and plant and machinery advance bear yearly interest at a rate based on the State Bank of India (SBI) Lending Rate (MCLR) for the Real State Sector. It also mentions that a 10% per annum simple interest rate applies to these advances. Therefore, material advances are interest-bearing. | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
What is the applicable percenatge of interest on the Material Advance? | The provided text mentions a 10% per annum interest rate on mobilization and plant and machinery advances. However, it does not specify an interest rate for material advances. | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 69 | Charge non-perishable, non-fragile and non-combustible and are in accordance with the contract and which have been brought on the site in connection therewith and are adequately stored and/or protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub-clause are incorporated in the work, the amount of such advance shall be recovered/ deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials. The decision of the Page 69 of 324 | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
Plant & Machinery Advance | Based on the provided text, a Plant & Machinery Advance can be given to the contractor if requested in writing within one month of bringing the plant and machinery to the site. The advance is granted for plant and machinery that, in the opinion of the Engineer-in-Charge, will expedite work and improve quality. The amount of the advance depends on the type of plant and equipment: * **Existing plant and machinery:** Up to 5% of the tender value. * **New plant and equipment:** Up to 90% of the price paid by the contractor (with proof provided). * **Second-hand/used plant and equipment:** Up to 50% of the depreciated value, as determined by the Engineer-in-Charge. The plant and equipment must be deemed necessary for the work by the Engineer-in-Charge, be in working order, and be hypothecated to WAPCOS before the advance is released. The contractor is responsible for maintaining the equipment and insuring it for replacement value. The advance bears 10% simple annual interest and is recovered through deductions from contractor bills after 10% of the gross work value is executed and paid. | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 71 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 This advance shall further be subject to the condition that such plant and equipment (a) are considered by the Engineer-in-Charge to be necessary for the works; (b) and are in working order and are maintained in working order; (c) hypothecated to the WAPCOS as specified by the Engineer-in-Charge before the payment of advance is released. The contractor shall not be permitted to remove from the site such hypothecated plant and equipment without the prior written permission of the Engineer- in-Charge. The contractor shall be responsible for maintaining such plant and equipment in good working order during the entire period of hypothecation failing which such advance shall be entirely recovered in lump sum. For this purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and
Is there a Provision for Plant and Machinery Advance? | Yes, there is a provision for a plant and machinery advance. The advance can be given if requested in writing within one month of bringing the plant and machinery to the site. The amount and conditions vary depending on whether the plant and machinery are new, used, or second-hand. | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and
What is the Percentage of Contract Value mentioned for the Plant and Machinery Advance? | The document states that the amount of advance for plant and machinery is restricted to 5% of the tender value. For new plant and equipment, it's 90% of the price paid by the contractor. For second-hand plant and equipment, it's 50% of the depreciated value. | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and
How many installments are there for the Plant and Machinery Advance? | The provided text doesn't specify the number of installments for the Plant and Machinery Advance. It only mentions that an advance *may* be given if requested, and that a bank guarantee is required. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What are the provisions for the receipt of the Plant and Machinery Advance? | An advance for plant, machinery, and shuttering material brought to the site may be given if requested in writing within one month of bringing the equipment. The advance is for items the Engineer-in-Charge deems will expedite work and improve quality. The amount is capped at 5% of the tender value for existing equipment. For new equipment, it's 90% of the purchase price (with proof of payment). For used equipment, it's 50% of the depreciated value, as determined by the Engineer-in-Charge. Further installments are released only after satisfactory utilization of previous installments is proven to the Engineer-in-Charge's satisfaction. A bank guarantee of 110% of the advance amount is required, valid for the contract period and renewed as needed. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and
What is the start date of the recovery of the Plant and Machinery Advance? | The recovery of the Plant and Machinery Advance starts after the first ten percent of the gross value of the work is executed and paid. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 71 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 This advance shall further be subject to the condition that such plant and equipment (a) are considered by the Engineer-in-Charge to be necessary for the works; (b) and are in working order and are maintained in working order; (c) hypothecated to the WAPCOS as specified by the Engineer-in-Charge before the payment of advance is released. The contractor shall not be permitted to remove from the site such hypothecated plant and equipment without the prior written permission of the Engineer- in-Charge. The contractor shall be responsible for maintaining such plant and equipment in good working order during the entire period of hypothecation failing which such advance shall be entirely recovered in lump sum. For this purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills
What is the time period in which Plant and Machinery Advance will be recovered? | The provided text states that recovery of the Plant and Machinery advance will be made by deduction from the contractor's bills, starting after 10% of the gross value of the work is executed and paid. The entire advance must be recovered by the time 80% of the gross value of the work is completed. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required
What are the Provisions for Bank Guarantee or letter of credit against Plant and Machinery Advance? | The provided text does not specify provisions for a bank guarantee or letter of credit against a plant and machinery advance. It only mentions that a bank guarantee is required for other types of advances. | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
what is the validity of Bank Guarantee or letter of credit provided against Plant and Machinery Advance? | The provided text does not specify the validity period of a bank guarantee or letter of credit for a plant and machinery advance. It only mentions that the bank guarantee must be kept renewed to cover the balance amount and likely period of complete recovery. | Page 70 | in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier installment to the entire satisfaction of the Engineer-in-Charge. Before any installment of advance is released, the contractor shall execute Bank Guarantee from a scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. This (Bank Guarantee from Scheduled Commercial Bank on prescribed format for the amount equal to 110% of the balance amount of advance) shall be kept renewed from time to time to cover the balance amount and likely period of complete recovery. (iii) PLANT MACHINERY & SHUTTERING MATERIAL ADVANCE An advance for plant, machinery & shuttering material required for the work and brought to site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and | Page 151 | This Guarantee will remain in force up to and including the date ……………………………… after the deadline for submission of Bids as is stated in the instructions to Bidders or as it may be extended by the ………………………………………… notice of which extension(s) to the Bank is hereby waived and notice to the bidder would constitute sufficient notice to the Bank. Any demand in respect of this guarantee should reach the Bank not later than the above date. Notwithstanding anything contained herein i) Liability under this guarantee shall not exceed …………………………………………… ii) This bank guarantee shall be valid upto ………………………………………… and; iii) Our liability to make payment shall arise and we are liable to pay the guaranteed amount or any part thereof under this guarantee only and only if you serve upon us a written claim or demand in terms of the guarantee on or before ……………………………………… (indicate a period twelve months after the date of issue of Bank Guarantee). | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the
is Plant and Machinery Advance interest bearing or interest free? | The provided text states that the Plant and Machinery Advance is interest-bearing. The interest rate varies depending on the clause: one clause specifies a 10% per annum simple interest rate, while another states that the interest rate will be based on the State Bank of India's (SBI) lending rate (MCLR) for the Real Estate sector. | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required
What is the applicable percenatge of interest on the Plant and Machinery Advance? | The provided text gives conflicting information regarding the interest rate on Plant and Machinery Advance. One section states it's the yearly interest rate and computing norms as per the State Bank of India (SBI) Lending Rate (MCLR), while another section specifies a simple interest rate of 10 percent per annum. | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 71 | purpose, steel scaffolding and form work shall be treated as plant and equipment. The contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site. Any amounts not recovered from the insurer will be borne by the contractor. (iv) INTEREST & RECOVERY The mobilization advance and plant and machinery advance in (ii) & (iii) above bear simple interest at the rate of 10 percent per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills commencing after first ten percent of the gross value of the work is executed and paid, on pro-rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the | Page 70 | amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required by the Engineer-in-Charge, submit the statement of value of such old plant and equipment duly approved by a Registered Valuer recognized by the Central Board of Direct Taxes under the Income- Tax Act, 1961. No such advance shall be paid on any plant and equipment of perishable nature and on any plant and equipment of a value less than Rs. 50,000/- Seventy five per cent of such amount of advance shall be paid after the plant & equipment is brought to site and balance twenty five percent on successfully commissioning the same. Leasing of equipment shall be considered at par with purchase of equipment and shall be covered by tripartite agreement with the following: 1. Leasing company which gives certificate of agreeing to lease equipment to the contractor. 2. Engineer in Charge, and
Schedule of Payments | Based on the provided text, at least 75% of the net amount of a submitted bill is to be paid within 10 working days. The remaining payment is due within 28 working days of bill submission, after final checking. A contractor may submit a payment request on the 5th business day of each month for work completed in the preceding month. The schedule of payments includes a schedule setting out each Milestone Event to be achieved in a month for the Works. Further details of the payment schedule are not provided in this excerpt. | Page 66 | rates as decided by the Engineer-in-Charge. An amount of ad-hoc payment not less than 75% of the net amount of the bill under check, shall be made within 10 working days of submission of the bill. The remaining payment is also to be made after final checking of the bill within 28 working days of submission of bill by the contractor. Page 66 of 324 | Page 113 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 From the date of issue of the Notice to Proceed, on the 5th (fifth) Business Day of any month, the Contractor may submit a Request for Payment, to WAPCOS Limited Representative in respect of the preceding month. Within each Request for Payment the Contractor shall show separately: (i) the amounts which the Contractor claims to be payable as the cost of the Works completed during that month; and (ii) the cumulative amount of all prior payments made by WAPCOS Limited; and (iii) any amounts to which the Contractor considers are due and payable to it in accordance with the provisions of the Contract. The Contractor’s Request for Payment shall: (i) be prepared on forms in the form and in a number advised by WAPCOS Limited Representative; and (ii) contain confirmation of the relevant Milestone Events which, in the opinion of the Contractor have been achieved in that month which applies to each such Milestone | Page 112 | specifications of the architects. b) All lighting installed by the contractor around the site and at the labour quarters during construction shall be CFL/LED bulbs of the appropriate illumination levels. This condition is a must, unless specifically prescribed. The contractor is expected to go through all other conditions of the GRIHA rating stipulations, which can be provided to him by the architects. Failure to adhere to any of the above mentioned items, without necessary clearances from the architects and the Engineer-in-charge, shall be deemed as a violation of contract and the contractor shall be held liable for penalty as determined by the architects. CLAUSE 44: PAYMENT 1. Payment Schedule The Payment Schedule includes a schedule setting out each Milestone Event to be achieved in a month for the Works. 2. Contractor ’s Application for Payment Page 112 of 324
What is the provision for release of the payment? | One-half of the retention money (or BG replacing it) is released upon issuance of the taking-over certificate (or proportionally if issued in parts). The other half is released 365 days after the defect liability period of the works or final payment, whichever is earlier, upon engineer certification. | Page 68 | that the contractor furnishes to the Engineer-in-Charge (1) an authorization in the form of a legally valid document such as a power of attorney conferring authority on the bank, registered financial, co-operative or thrift societies or recognized financial institutions to receive payments and (2) his own acceptance of the correctness of the amount made out as being due to him by Government or his signature on the bill or other claim preferred against Government before settlement by the Engineer-in-Charge of the account or claim by payment to the bank, registered financial, co- operative or thrift societies or recognized financial institutions. While the receipt given by such banks registered financial, co-operative or thrift societies or recognized financial institutions shall constitute a full and sufficient discharge for the payment, the contractor shall whenever possible present his | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 113 | Works which was included in the immediately preceding Certificates of Payment was paid all amounts then due to it for such Works (k) The Contractor providing evidence of the validity of the Contractor’s Insurances. CLAUSE 45: PREFERENCE TO MAKE IN INDIA Page 113 of 324
What are the Price Weightages with respect to completion of activities? | I'm sorry, but this document does not contain information about price weightages with respect to the completion of activities. The provided text focuses on rate determination for deviations and variations in contract work, not on weightages for activity completion. | Page 74 | 12.3 DETERMINATION OF RATES In the event, there is any deviations/variations in work as defined in the contract, the contractor shall submit the complete proposal to Engineer-in-charge within 15 days duly supported with :- a) Analysis of rates for items involved, along with relevant documents, rates of materials, tools/plants and labour, etc. b) The impact, if any, which the deviations/variations is likely to have on the project completion schedule, On receipt of such proposal, either individually or covering group of items, the Engineer- in- charge shall examine the proposal regarding its admissibility and finalize the proposal/rates within 45 days after receipt of proposal with all requisite details and documents from the contractors, after giving due consideration to the proposal, analysis and rates of materials and labours, etc. 12.3.1 The increase/decrease in the rates due to deviations/variations shall be decided based on the following criteria:- | Page 75 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 b) If the item of work as stipulated in the schedule of quantity/scope of work deviates on minus side, then the amount for such deviated quantity shall be deducted proportionately at the agreement rate. p) Pricing of variations If there are changes in the quantity/specifications/ alterations/ substitutions/additions, etc. in the items, other than mentioned in para- (i) above, the rates shall be determined based on detailed analysis of rates with original stipulated scope of items & newly proposed/provided items. The difference of rates so determined shall be payable to/ recoverable from the contractor. The rates for both the components i.e. materials &labour shall be based on prevailing market rates. The rate finalized by the Engineer- in-Charge shall be final and binding. 12.3.2 In case of either non-submission of timely proposal or incomplete proposal by the contractor | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall
What is the date for Submission of Running Account Bill or Interim Payment Certificate? | The provided text states that running account bills should be submitted by the contractor on or before the date of every month fixed by the Engineer-in-Charge. The specific date is not provided. | Page 66 | It is also a term of this contract that checking and/or test checking the measurements of any item of work in the measurement book and/or its payment in the interim, on account of final bill shall not be considered as conclusive evidence as to the sufficiency of any work or material to which it relates nor shall it relieve the contractor from liabilities from any over measurement or defects noticed till completion of the defects liability period. CLAUSE 7 : PAYMENT ON INTERMEDIATE CERTIFICATE TO BE REGARD AS ADVANCE The running account bills shall be submitted by the contractor for the work executed on the basis of such recorded measurements as per Clause 6 on the format of the WAPCOS in triplicate on or before the date of every month fixed for the same by the Engineer-in-Charge. The contractor shall not be entitled to be paid any such interim payment if the gross work done together with net payment/ | Page 123 | in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the laws of India and the Parties submit to sole & exclusive jurisdiction of courts at Delhi.” New Clause-1 Minimum Amount of Running Account Bill The Contractor shall periodically submit Running Account (RA) bills for the gross work done not be less than Rs 1.50 Cr. for Construction. All running bills shall be accompanied with the Geo-tagged (GPS) clear photographs in sufficient number and angles illustrating the progress of work and for which claims raised in RA bill. The photographs shall be duly signed by the Contract or. The contractor shall submit the bill in the standard format agreed by the SMFPL/ WAPCOS 2.0 ADDITIONAL CONDITIONS OF CONTRACT Page 123 of 324 | Page 66 | not be entitled to be paid any such interim payment if the gross work done together with net payment/ adjustment of advances for material collected, if any, since the last such payment is less than the amount specified in Special Conditions of Contract, in which case the interim bill shall be prepared on the appointed date of the month after the requisite progress is achieved. Engineer- in-Charge shall arrange to have the bill verified In the event of the failure of the contractor to submit the bills, no claims whatsoever due to delays on payment including that of interest shall be payable to the contractor. Payment on account of amount admissible shall be made by the Engineer- in-Charge certifying the sum to which the contractor is considered entitled by way of interim payment at such rates as decided by the Engineer-in-Charge. An amount of ad-hoc payment not less than 75% of the net amount of the bill under check, shall be
What is the duration for Certification of Running Account or Interim Payment Certificate? | The provided text does not specify a duration for the certification of running account or interim payment certificates. It only states that running account bills should be submitted by the contractor on or before a date fixed by the Engineer-in-Charge, and that payment will be made after verification. | Page 66 | It is also a term of this contract that checking and/or test checking the measurements of any item of work in the measurement book and/or its payment in the interim, on account of final bill shall not be considered as conclusive evidence as to the sufficiency of any work or material to which it relates nor shall it relieve the contractor from liabilities from any over measurement or defects noticed till completion of the defects liability period. CLAUSE 7 : PAYMENT ON INTERMEDIATE CERTIFICATE TO BE REGARD AS ADVANCE The running account bills shall be submitted by the contractor for the work executed on the basis of such recorded measurements as per Clause 6 on the format of the WAPCOS in triplicate on or before the date of every month fixed for the same by the Engineer-in-Charge. The contractor shall not be entitled to be paid any such interim payment if the gross work done together with net payment/ | Page 67 | with the contract and specifications. Any such interim payment, or any part thereof shall not in any respect conclude, determine or affect in any way powers of the Engineer- in-Charge under the contract or any of such payments be treated as final settlement and adjustment of accounts or in any way vary or affect the contract. Pending consideration of extension of date of completion, interim payments shall continue to be made as herein provided without prejudice to the right of the WAPCOS to take action under the terms of this contract for delay in the completion of work, if the extension of date of completion is not granted by the competent authority. Clause 7A No Running Account Bill shall be paid for the work till the applicable labour licenses, registration with EPFO, ESIC and BOCW Welfare Board, whatever applicable are submitted by the contractor to the Engineer-in-Charge. CLAUSE 8 : COMPLETION CERTIFICATE AND COMPLETION PLANS | Page 66 | not be entitled to be paid any such interim payment if the gross work done together with net payment/ adjustment of advances for material collected, if any, since the last such payment is less than the amount specified in Special Conditions of Contract, in which case the interim bill shall be prepared on the appointed date of the month after the requisite progress is achieved. Engineer- in-Charge shall arrange to have the bill verified In the event of the failure of the contractor to submit the bills, no claims whatsoever due to delays on payment including that of interest shall be payable to the contractor. Payment on account of amount admissible shall be made by the Engineer- in-Charge certifying the sum to which the contractor is considered entitled by way of interim payment at such rates as decided by the Engineer-in-Charge. An amount of ad-hoc payment not less than 75% of the net amount of the bill under check, shall be
When payment will be released? | Based on the provided text, payments are released by WAPCOS to the contractor in the following manner: * **Request for Payment:** The contractor submits a request for payment on the 5th business day of each month for the preceding month's work. This request must detail the cost of completed work, cumulative payments received, and any other amounts due. * **WAPCOS Payment to Contractor:** WAPCOS will make payments to the contractor on a back-to-back basis, meaning 45 days after receiving payment from the principal employer (SMFPL). If WAPCOS doesn't receive payment from SMFPL, they are not responsible for paying the contractor. Payments are made via RTGS e-transfer. * **Retention Money Release:** Half of the retention money (or bank guarantee) is released upon issuance of the taking-over certificate. The other half is released 365 days after the defect liability period (DLP) of the works or final payment, whichever is earlier. | Page 113 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 From the date of issue of the Notice to Proceed, on the 5th (fifth) Business Day of any month, the Contractor may submit a Request for Payment, to WAPCOS Limited Representative in respect of the preceding month. Within each Request for Payment the Contractor shall show separately: (i) the amounts which the Contractor claims to be payable as the cost of the Works completed during that month; and (ii) the cumulative amount of all prior payments made by WAPCOS Limited; and (iii) any amounts to which the Contractor considers are due and payable to it in accordance with the provisions of the Contract. The Contractor’s Request for Payment shall: (i) be prepared on forms in the form and in a number advised by WAPCOS Limited Representative; and (ii) contain confirmation of the relevant Milestone Events which, in the opinion of the Contractor have been achieved in that month which applies to each such Milestone | Page 121 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added Contract Agreement (if work is awarded to bidder) shall be made proportionately by WAPCOS only on back to back basis i.e., after 45 days subject to receipt of payment from SMFPL being Principal Employer. The Bidder also unconditionally agree that in the ev ent the, payment or part thereof, under the present Tender and Work Order/ Contract Agreement (if work is awarded to bidder) is not received from SMFPL, then WAPCOS &/or any of its Employee/ Officer shall not be responsible to pay any amount to Bidder. The said condition shall supersede any and all other conditions of Tender and Work Order/ Contract Agreement between the parties (if work is awarded to bidder). All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest
What is the percentage of the initial payment release? | The provided text states that a 10% mobilization advance is paid upon submission of a Standby Letter of Credit (SBLC). This is then paid out in installments as described in the Note section. There is no single initial payment percentage mentioned. | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in | Page 323 | iii. 2.7%: After completion of 17 th Floor slab iv. 2.7%: After completion of 20th Floor slab v. 2.7%: After completion of 17th /22nd /24th (as applicable) vi. 2.7%: After completion of Roof slab vii. 2.7%: After completion of all activities above roof (Water Tank etc.) D. Brick Work/ Walling Works i. 2.7%: After completion till 10 th floor ii. 2.7%: After completion of rest E. Plastering i. 3%: After completion till 10 th floor ii. 4%: After completion of rest along with Plinth protection, including roof treatment, completion of all other related services & works, etc. F. Finishing 10%: After completion & successful operation of all Finishing items including all Flooring, Walling, Painting (both internal and external), doors, aluminum windows, protective iron/steel grill, all security system, all HVAC system, CCTV system, calling bell system, Intercom facility, other related services & works, etc. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest
What is the duration for the release of initial payment? | The provided text does not specify a duration for the release of the initial payment. It mentions that one-half of the retention money (or BG) is released upon issuance of the taking-over certificate, and the other half is released 365 days after the DLP of the works or final payment, whichever is earlier. However, there is no information about the timing of the initial payment itself. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 122 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added the work is executed and paid, on pro -rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time eighty percent of the gross value of the contract is executed and paid, together with interest due on the entire outstanding amount up to the date of recovery of the installment. Clause 17 Damages and Defect Liability Period Applicable Added/Modified: 2(Two) years from the date of successful completion of works as recorded by the Engineer -In- Charge and compliance of defects/ rectifications/ observations of SMFPL/WAPCOS before taking over, getting of all NoCs / clearances / Occupancy Cert ificate from Local Department, and successfully handing over with all satisfaction along with submission of all the required documents i.e. As - built drawings (minimum 3 | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in
What is the duration for the release of final payment? | The final payment (half of the retention money or BG) will be released 365 days after the Defect Liability Period (DLP) of the works or final payment, whichever is earlier. If different sections have different DLPs, the latest DLP applies. | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 68 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 is more as may be fixed by the authority as mentioned in Schedule F and in this respect the decision of the that authority shall be final and binding on the contractor. CLAUSE 9 : PAYMENT OF FINAL BILL The final bill shall be submitted by the contractor in the same manner as specified in interim bills within three months of physical completion of the work or within one month of the date of the final certificate of completion furnished by the Engineer-in-Charge whichever is earlier. No further claims shall be made by the contractor after submission of the final bill and these shall be deemed to have been waived and extinguished. Payments of those items of the bill in respect of which there is no dispute and of items in dispute, for quantities and rates as approved by Engineer-in-Charge, will, as far as possible be made within the period of three months the period being reckoned from the date | Page 323 | iii. 2.7%: After completion of 17 th Floor slab iv. 2.7%: After completion of 20th Floor slab v. 2.7%: After completion of 17th /22nd /24th (as applicable) vi. 2.7%: After completion of Roof slab vii. 2.7%: After completion of all activities above roof (Water Tank etc.) D. Brick Work/ Walling Works i. 2.7%: After completion till 10 th floor ii. 2.7%: After completion of rest E. Plastering i. 3%: After completion till 10 th floor ii. 4%: After completion of rest along with Plinth protection, including roof treatment, completion of all other related services & works, etc. F. Finishing 10%: After completion & successful operation of all Finishing items including all Flooring, Walling, Painting (both internal and external), doors, aluminum windows, protective iron/steel grill, all security system, all HVAC system, CCTV system, calling bell system, Intercom facility, other related services & works, etc.
What is the interest in case of delay in the release of the payment? | The provided text specifies the interest rate and calculation method for mobilization advances and plant and machinery advances (Clause 10 B(ii) & 10B (iii)). These advances accrue yearly interest based on the State Bank of India (SBI) Lending Rate (MCLR) and other SBI provisions for the Real Estate sector. Interest is calculated from the payment date to the recovery date, inclusive. However, there is no information about interest in case of a delay in the *release* of payments outside of these specific advance types. | Page 121 | Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in two instalments. The first instalment of 5% of tendered value shall be paid on commencement of the work at site. The second instalment of 5% of tendered value shall be paid after achiev ing the financial progress of 10 (ten) percent of the contract price. Clause 10 B(iv) Interest and Recovery The mobilization advance and plant and machinery advance in clause 10B (ii) & 10B (iii) above bears yearly interest. The yearly interest rate and computing norms shall be as per State Bank of India (SBI) Lending Rate (MCLR) and other provisions of SBI for Real State Sector and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance. Recovery of such sums advanced shall be made by the deduction from the contractors bills | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 121 | All payments shall be released by way of e-transfer through RTGS in India directly at their Bank account by WAPCOS Clause 10 B(i) Secured Advance on Non- Perishable Materials Applicable 75% of the assessed value of material. Secured Advance shall be recovery as per the consumption of material for which secured advance was given to the contractor by the deducting from the contractors bills. Clause 10 B(ii) Mobilization Advance 10% of the tender ed value on submission of Standby Letter of Credit (SBLC) from Nationalised/ Scheduled commercial Bank for the amount equal to 110% of the amount of advance and valid for the contract period. The Yearly interest rate and computing norms shall be as per SBI Lending Rate (MCLR) and other provisions of SBI for Real State Sector . The interest shall be calculated from the date of payment to the date of recovery both days inclusive. Note: Above 10% Mobilization Advance shall be paid in
What is the minimum amount for raising of Running Account Bill or Interim Payment Certificate? | The minimum amount for a Running Account (RA) bill for construction is Rs 1.50 Cr. For interim payments, if the gross work done plus net payment/adjustment of advances is less than the amount specified in the Special Conditions of Contract, no interim payment will be made until the requisite progress is achieved. | Page 123 | in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the laws of India and the Parties submit to sole & exclusive jurisdiction of courts at Delhi.” New Clause-1 Minimum Amount of Running Account Bill The Contractor shall periodically submit Running Account (RA) bills for the gross work done not be less than Rs 1.50 Cr. for Construction. All running bills shall be accompanied with the Geo-tagged (GPS) clear photographs in sufficient number and angles illustrating the progress of work and for which claims raised in RA bill. The photographs shall be duly signed by the Contract or. The contractor shall submit the bill in the standard format agreed by the SMFPL/ WAPCOS 2.0 ADDITIONAL CONDITIONS OF CONTRACT Page 123 of 324 | Page 66 | not be entitled to be paid any such interim payment if the gross work done together with net payment/ adjustment of advances for material collected, if any, since the last such payment is less than the amount specified in Special Conditions of Contract, in which case the interim bill shall be prepared on the appointed date of the month after the requisite progress is achieved. Engineer- in-Charge shall arrange to have the bill verified In the event of the failure of the contractor to submit the bills, no claims whatsoever due to delays on payment including that of interest shall be payable to the contractor. Payment on account of amount admissible shall be made by the Engineer- in-Charge certifying the sum to which the contractor is considered entitled by way of interim payment at such rates as decided by the Engineer-in-Charge. An amount of ad-hoc payment not less than 75% of the net amount of the bill under check, shall be | Page 36 | Engineer and details will be submitted with each Bill. We shall not raise any objection if deduction is made for the same from Running Bills. Date: (Signature, Name, Designation of the Authorized signatory with Seal) Place: Page 36 of 324
What are the maximum numbers for raising Running Account Bill or Interim Payment Certificate? | The provided text does not specify a maximum number of Running Account Bills or Interim Payment Certificates. It only states that the minimum amount for a Running Account bill for construction is Rs 1.50 Cr. | Page 36 | Engineer and details will be submitted with each Bill. We shall not raise any objection if deduction is made for the same from Running Bills. Date: (Signature, Name, Designation of the Authorized signatory with Seal) Place: Page 36 of 324 | Page 123 | in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the laws of India and the Parties submit to sole & exclusive jurisdiction of courts at Delhi.” New Clause-1 Minimum Amount of Running Account Bill The Contractor shall periodically submit Running Account (RA) bills for the gross work done not be less than Rs 1.50 Cr. for Construction. All running bills shall be accompanied with the Geo-tagged (GPS) clear photographs in sufficient number and angles illustrating the progress of work and for which claims raised in RA bill. The photographs shall be duly signed by the Contract or. The contractor shall submit the bill in the standard format agreed by the SMFPL/ WAPCOS 2.0 ADDITIONAL CONDITIONS OF CONTRACT Page 123 of 324 | Page 66 | It is also a term of this contract that checking and/or test checking the measurements of any item of work in the measurement book and/or its payment in the interim, on account of final bill shall not be considered as conclusive evidence as to the sufficiency of any work or material to which it relates nor shall it relieve the contractor from liabilities from any over measurement or defects noticed till completion of the defects liability period. CLAUSE 7 : PAYMENT ON INTERMEDIATE CERTIFICATE TO BE REGARD AS ADVANCE The running account bills shall be submitted by the contractor for the work executed on the basis of such recorded measurements as per Clause 6 on the format of the WAPCOS in triplicate on or before the date of every month fixed for the same by the Engineer-in-Charge. The contractor shall not be entitled to be paid any such interim payment if the gross work done together with net payment/
Liquidity Damages | Based on the provided text, Liquidity Damages are a compensation for delay. If the contractor fails to complete the work by the contract's completion date (or any extended date), they will pay a sum not less than 1% of the Tendered Value for each week of delay, up to a maximum of 10% of the Contract Price. These damages will be recovered from upcoming interim bills or the final bill. If those bills are insufficient to cover the full amount of the damages, the remaining balance will be recovered from the Performance Security, Security Deposit, and any other financial deposits the contractor has with the Employer. | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 44 | the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to terminate the contract according to Section 3, the Employer shall be entitled to demand and recover from the contractor liquidated damages of the contract value or the amount equivalent to Performance Bank Guarantee. Section 5 – Previous transgression Bidder declares that no previous transgressions occurred in the last three years with any other Company in any country conforming to the anti-corruption approach or with any Public Sector Enterprise in India that could justify his exclusion from the tender process. Page 44 of 324
What is the Applicable Percentage for Liquidity Damages or Penalty? | The applicable percentage for liquidity damages is 1% of the tendered value for each week of delay, up to a maximum of 10% of the contract price. | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest
What is the maximum limit for Liquidity Damages or Penalty? | The maximum limit for Liquidity Damages is 10% of the Contract Price. | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of | Page 44 | an accessory to such offences. Section 3 – Disqualification from tender process and exclusion from future contracts If the ‘Bidder/ Contractor’, before award or during execution, has committed a transgression through a violation of Section 2, above or in any other form such as to put their reliability or credibility in question, the Employer is entitled to disqualify the ‘Bidder/ Contractor’ from the tender process or take action as per the procedure mentioned in the “Guidelines on Banning of business dealings”. Section 4 – Compensation for Damages If the Employer has disqualified the ‘Bidder/ Contractor’ from the tender process prior to the award according to Section 3, the Employer is entitled to demand and recover from ‘Bidder/ Contractor’ the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to
What is the provision for release of Liquidity Damages or Penalty? | If the contractor fails to complete the work by the deadline, liquidity damages (not less than 1% of the tendered value per week, up to a maximum of 10% of the contract price) will be imposed. These damages will be recovered from upcoming interim or final bills. If the bills are less than the total liquidity damage amount, the remaining balance will be recovered from the contractor's performance security, security deposit, and other financial deposits. | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 59 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 After approval of SMFPL, the Security Deposit shall be released as applicable. CLAUSE 2: COMPENSATION FOR DELAY i.e. LIQUIDITY DAMAGES If the contractor fails to maintain the required progress or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under purview of the Contract on account of such breach, pay compensation for delay i.e. Liquidity Damage, a sum not less than 1.0% (One percent) of the Tendered Value as aforesaid for each week and limited to 10% of the Contract Price. In case Liquidity Damage imposed by Principal Employer to the project at any point of time, then full amount of Liquidity Damage (10% of the Contract Price) will be recovered from the up-coming interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of
Bonus clause or Incentive for early Completion | Clause 2A, titled "Incentive for Early Completion," is not applicable in this tender (WAP/CMU-III/2024-25/SMFPL/Agartala/09). | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 120 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added Clause 2 Compensation for Delay / Liquidity Damage Applicable 0.50% of the cost of Contract price per week. (Maximum up to 10% of the Contract price). Milestones to be Achieved: SN. Description of Mile stone (Physical) Time allowed (from the date of start) Amoun to be withheld on on failure to achieve milestone 1 1/8th of whole of the work Within 12 months 10% of 1/8 th of the value of Tender accepted 2 3/8th of whole of the work Within 24 months 10% of 3/8th of the value of Tender accepted 3 ¾th of whole of the work Within 36 months 10% of ¾th of the value of Tender accepted 4 Whole of the work Within 48 months 10% of the value of Tender accepted or Completion cost whichever is higher. Clause 2A Incentive for Early Completion Not Applicable Clause 5 Time and Extension for Delay Applicable | Page 120 | 10% of the value of Tender accepted or Completion cost whichever is higher. Clause 2A Incentive for Early Completion Not Applicable Clause 5 Time and Extension for Delay Applicable Commencement of work 15 days from date of award Stipulated time of completion of project As Mentioned in NIT Clause 7 Payment on Intermediate Certificate to be regarded as advance Applicable Clause 7A No Running Account Bill shall be paid for the work till the applicable labour licenses ………. Applicable New Clause 7B (Added) Payment The Bidder (Contractor) acknowledges that under the present Tender and Work Order/ Contract Agreement (if work is awarded to bidder), WAPCOS is only w orking as intermediary between SMFPL being Principal Employer. Thus the bidder unconditionally acknowledges that the payments under the present Tender and Work Order/ Page 120 of 324
What is the provision for Bonus or Incentive for early Completion? | Clause 2A, Incentive for Early Completion, is not applicable in this tender (WAP/CMU-III/2024-25/SMFPL/Agartala/09). | Page 59 | interim bills/ final bill. If the amount of up-coming interim bills/ final bill is less than the amount of Liquidity Damage, then balance amount of Liquidity Damage will be recovered from the Performance Security, Security Deposit and any other financial deposit of Contractor with Employer. CLAUSE 2A: INCENTIVE FOR EARLY COMPLETION -----NOT APPLICABLE In case, the contractor completes the work ahead of updated stipulated date of completion considering the effect of extra work (to be calculated on pro-rata basis as cost of extra work X stipulated period/tendered cost), a bonus @ 1% (one per cent) of the tendered value per month computed on per day basis, shall be payable to the contractor, subject to a maximum limit of 5% (five per cent) of the tendered value. The amount of bonus, if payable, shall be paid along with final bill after completion of work. Provided always that provision of the Clause 2A shall be applicable | Page 120 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 Clause No. Description Applicability/Modified/ Added Clause 2 Compensation for Delay / Liquidity Damage Applicable 0.50% of the cost of Contract price per week. (Maximum up to 10% of the Contract price). Milestones to be Achieved: SN. Description of Mile stone (Physical) Time allowed (from the date of start) Amoun to be withheld on on failure to achieve milestone 1 1/8th of whole of the work Within 12 months 10% of 1/8 th of the value of Tender accepted 2 3/8th of whole of the work Within 24 months 10% of 3/8th of the value of Tender accepted 3 ¾th of whole of the work Within 36 months 10% of ¾th of the value of Tender accepted 4 Whole of the work Within 48 months 10% of the value of Tender accepted or Completion cost whichever is higher. Clause 2A Incentive for Early Completion Not Applicable Clause 5 Time and Extension for Delay Applicable | Page 70 | site by the Contractor may be given if requested by the contractor in writing within one month of bringing such plant and machinery to site. Such advance shall be given on such plant and machinery which in the opinion of the Engineer-in-charge will add to the expeditious execution of work and improve the quality of work. The amount of advance shall be restricted to 5% percent of the tender value. In the case of new plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge. In the case of second hand and used plants and equipment, the amount of such advance shall be limited to 50% of the depreciated value of plant and equipment as may be decided by the Engineer-in-Charge. The contractor shall, if so required
Price variation or Escalation | Based on the provided text, if the prices of materials (excluding those supplied or services rendered at fixed prices by WAPCOS as per clauses 10 & 34) and/or labor wages increase during the contract's execution, the contractor will be compensated. This compensation is detailed in the document and applies only to work done within the stipulated contract period, including any justified extensions (under clause 5, excluding clause 2 actions). For work during justified extensions, compensation is limited to prices/wages at the updated completion date. The method for determining price increases for specific materials (cement, steel, POL, etc.) involves using price indices from the Economic Advisor to the Government of India, Ministry of Commerce and Industry. For other materials, the All India Wholesale Price Indices will be used. Base prices are determined by state/central government issuances. | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect | Page 74 | and labours, etc. 12.3.1 The increase/decrease in the rates due to deviations/variations shall be decided based on the following criteria:- o) Pricing of deviations a) If the item of work as stipulated in the schedule of quantity/scope of work deviates on plus side, then the rate for the deviated quantity shall be paid at the agreement rate upto the deviation limit as specified in Special Condiiotns of Contract with the same terms & conditions of the contract. Beyond deviation limit as specified in the Special Condiiotns of Contract, rate shall be payable on market rates to be determined based on the relevant documents and prevailing market rates, as per Para (ii) below Page 74 of 324 | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall
What is the fixed amount or the percentage of the Contract for Price variation or Escalation? | The provided text does not specify a fixed amount or percentage for price variation or escalation. It describes the conditions under which compensation will be provided for increases in material prices and/or labor wages, but the calculation method is referenced to Clause 10CA of the General Conditions of Contract, which is not included in this text. | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect | Page 71 | materials covered under Clause 10CA and not being a material supplied from the Engineer- in- Charge’s stores in accordance with Clause 10 thereof) and/or wages of labour increases as a direct result of the coming into force of any fresh law, or statutory rule or order (but not due to any changes of rate in sales tax/VAT, Central/State Excise/Custom Duty) beyond the prices/wages prevailing at the time of the last stipulated date of receipt of tenders including extensions, if any, for the work during contract period including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2, then the amount of the contract shall accordingly be varied and provided further that any such increase shall be limited to the price/wages prevailing at the time of updated stipulated date of completion considering effect of extra work (extra time to be calculated on | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324
What is the Start Date for Price variation or Escalation? | The provided text does not specify a start date for price variation or escalation. It only describes how price increases will be compensated, referencing the "last stipulated date of receipt of tenders including extensions, if any". | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 71 | materials covered under Clause 10CA and not being a material supplied from the Engineer- in- Charge’s stores in accordance with Clause 10 thereof) and/or wages of labour increases as a direct result of the coming into force of any fresh law, or statutory rule or order (but not due to any changes of rate in sales tax/VAT, Central/State Excise/Custom Duty) beyond the prices/wages prevailing at the time of the last stipulated date of receipt of tenders including extensions, if any, for the work during contract period including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2, then the amount of the contract shall accordingly be varied and provided further that any such increase shall be limited to the price/wages prevailing at the time of updated stipulated date of completion considering effect of extra work (extra time to be calculated on
What is the Base Dateor Base Month for Price variation or Escalation? | The provided text states that the base price for cement, steel reinforcement, structural steel, and POL (petroleum, oil, and lubricants) shall be as issued by the state/Central Government from time to time. It does not specify a single base date or month. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect
What is Labour component considered for Price variation or Escalation? | The labor component of the work executed during a period is considered as a percentage of the value of work done during that period, as specified in the Special Conditions of Contract. Increases or decreases in labor costs are based on the minimum daily wage of an unskilled adult male mazdoor, as fixed by law, statutory rule, or order. | Page 72 | of clause 5 of the contract without any action under clause 2. Engineer-in-Charge may call books of account and other relevant documents from the contractor to satisfy himself about reasonability of increase in prices of materials and wages. The contractor shall, within a reasonable time of his becoming aware of any alteration in the price of any such materials and/or wages of labour, give notice thereof to the Engineer-in-Charge stating that the same is given pursuant to this condition together with all information relating thereto which he may be in position to supply. For this purpose, the labour component of the work executed during period under consideration shall be the percentage as specified in Special Conditions of Contract, of the value of work done during that period and the increase/decrease in labour shall be considered on the minimum daily wages in rupees of any unskilled adult male mazdoor, fixed under any law, statutory rule or order. | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 72 | during that period and the increase/decrease in labour shall be considered on the minimum daily wages in rupees of any unskilled adult male mazdoor, fixed under any law, statutory rule or order. CLAUSE 10CA :PAYMENT DUE TO VARIATION IN PRICES OF MATERIALS AFTER RECEIPT OF TENDER If after submission of the tender, the price of materials specified in Special Conditions of Contract increases/ decreases beyond the base price(s) as indicated in Special Conditions of Contract for the work, then the amount of the contract shall accordingly be varied and provided further that any such variations shall be effected for stipulated period of Contract including the justified period extended under the provisions of Clause 5 of the Contract without any action under Clause 2. However for work done/during the justified period extended as above, it will be limited to indices prevailing at the time of updated stipulated date of completion considering the effect of extra work
What is Cement component considered for Price variation or Escalation? | The price variation or escalation for cement will be determined by the Price Indices of the Economic Advisor to the Government of India, Ministry of Commerce and Industry. The base price will be as issued by the state/Central Government from time to time. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect
What is Steel component considered for Price variation or Escalation? | The price variation for steel reinforcement and structural steel will be determined by the Price Indices of the Economic Advisor to the Government of India, Ministry of Commerce and Industry. The base price will be as issued by the state/Central Government from time to time. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 72 | of clause 5 of the contract without any action under clause 2. Engineer-in-Charge may call books of account and other relevant documents from the contractor to satisfy himself about reasonability of increase in prices of materials and wages. The contractor shall, within a reasonable time of his becoming aware of any alteration in the price of any such materials and/or wages of labour, give notice thereof to the Engineer-in-Charge stating that the same is given pursuant to this condition together with all information relating thereto which he may be in position to supply. For this purpose, the labour component of the work executed during period under consideration shall be the percentage as specified in Special Conditions of Contract, of the value of work done during that period and the increase/decrease in labour shall be considered on the minimum daily wages in rupees of any unskilled adult male mazdoor, fixed under any law, statutory rule or order.
What is Structural Steel component considered for Price variation or Escalation? | Based on the provided text, structural steel is considered for price variation or escalation. The increase/decrease in its price will be determined by the Price indices from the Economic Advisor to the Government of India, Ministry of Commerce and Industry. The base price will be as issued by the state/Central Government. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 101 | (b) Theoretical quantity of steel reinforcement or structural steel sections shall be taken as the quantity required as per design or as authorized by Engineer- in-Charge, including authorized lappages, chairs etc. plus 3% wastage due to cutting into pieces, such theoretical quantity being determined and compared with the actual issues each diameter wise, section wise and category wise separately. (c) Theoretical quantity of G.I. & C.I. or other pipes, conduits, wires and cables, pig lead and G.I./M.S. sheets shall be taken as quantity actually required and measured plus 5% for wastage due to cutting into pieces (except in the case of G.I./M.S. sheets it shall be 10%), such determination & comparison being made diameter wise & category wise. (d) For any other material as per actual requirements. Over the theoretical quantities of materials so computed a variation shall be allowed as
What is Bitumen component considered for Price variation or Escalation? | Based on the provided text, bitumen is considered for price variation or escalation. The text specifies that the quantity of bitumen will be calculated based on the quantity required for different work items as shown in the Schedule of Rates. Price increases/decreases are determined using price indices from the Economic Advisor to the Government of India, Ministry of Commerce and Industry, or a similar index if one is not available for bitumen. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 101 | (i) After completion of the work and also at any intermediate stage in the event of non- reconciliation of materials issued, theoretical quantity of materials used in the work shall be calculated on the basis and method given hereunder: (a) Quantity of cement & bitumen shall be calculated on the basis of quantity of cement & bitumen required for different items of work as shown in the Schedule of Rates mentioned in Special Conditions of Contract. In case any item is executed for which standard constants for the consumption of cement or bitumen are not available in the above mentioned schedule/statement or cannot be derived from the same shall be calculated on the basis of standard formula to be laid down by the Engineer-in-Charge. (b) Theoretical quantity of steel reinforcement or structural steel sections shall be taken as the quantity required as per design or as authorized by Engineer- in-Charge, including | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324
What is fuel and lubricants component considered for Price variation or Escalation? | The provided text states that the increase/decrease in prices of "POL" (presumably Petroleum, Oil, and Lubricants) will be determined by the Price indices of the Economic Advisor to the Government of India, Ministry of Commerce and Industry. The base price will be as issued by the state/Central Government. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 74 | and labours, etc. 12.3.1 The increase/decrease in the rates due to deviations/variations shall be decided based on the following criteria:- o) Pricing of deviations a) If the item of work as stipulated in the schedule of quantity/scope of work deviates on plus side, then the rate for the deviated quantity shall be paid at the agreement rate upto the deviation limit as specified in Special Condiiotns of Contract with the same terms & conditions of the contract. Beyond deviation limit as specified in the Special Condiiotns of Contract, rate shall be payable on market rates to be determined based on the relevant documents and prevailing market rates, as per Para (ii) below Page 74 of 324 | Page 74 | 12.3 DETERMINATION OF RATES In the event, there is any deviations/variations in work as defined in the contract, the contractor shall submit the complete proposal to Engineer-in-charge within 15 days duly supported with :- a) Analysis of rates for items involved, along with relevant documents, rates of materials, tools/plants and labour, etc. b) The impact, if any, which the deviations/variations is likely to have on the project completion schedule, On receipt of such proposal, either individually or covering group of items, the Engineer- in- charge shall examine the proposal regarding its admissibility and finalize the proposal/rates within 45 days after receipt of proposal with all requisite details and documents from the contractors, after giving due consideration to the proposal, analysis and rates of materials and labours, etc. 12.3.1 The increase/decrease in the rates due to deviations/variations shall be decided based on the following criteria:-
What is Plant, Machinery and tool component considered for Price variation or Escalation? | I'm sorry, but this document does not contain information on how plant, machinery, and tool components are considered for price variation or escalation. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 71 | materials covered under Clause 10CA and not being a material supplied from the Engineer- in- Charge’s stores in accordance with Clause 10 thereof) and/or wages of labour increases as a direct result of the coming into force of any fresh law, or statutory rule or order (but not due to any changes of rate in sales tax/VAT, Central/State Excise/Custom Duty) beyond the prices/wages prevailing at the time of the last stipulated date of receipt of tenders including extensions, if any, for the work during contract period including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2, then the amount of the contract shall accordingly be varied and provided further that any such increase shall be limited to the price/wages prevailing at the time of updated stipulated date of completion considering effect of extra work (extra time to be calculated on | Page 72 | of clause 5 of the contract without any action under clause 2. Engineer-in-Charge may call books of account and other relevant documents from the contractor to satisfy himself about reasonability of increase in prices of materials and wages. The contractor shall, within a reasonable time of his becoming aware of any alteration in the price of any such materials and/or wages of labour, give notice thereof to the Engineer-in-Charge stating that the same is given pursuant to this condition together with all information relating thereto which he may be in position to supply. For this purpose, the labour component of the work executed during period under consideration shall be the percentage as specified in Special Conditions of Contract, of the value of work done during that period and the increase/decrease in labour shall be considered on the minimum daily wages in rupees of any unskilled adult male mazdoor, fixed under any law, statutory rule or order.
What is other materials component considered for Price variation or Escalation? | For materials not covered under Clause 10CA, the All India Wholesale Price Indices of materials as published by the Economic Advisor to the Government of India, Ministry of Commerce and Industry will be used to determine price increases or decreases. If a specific material's price index isn't available from the Ministry, the index of the nearest similar material (as specified in the Special Conditions of Contract) will be used. | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 73 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 If the prices of materials (not being materials supplied or services rendered at fixed prices by the WAPCOS in accordance with clause 10 & 34 thereof) and/or wages of labour required for execution of the work increase, the contractor shall be compensated for such increase as per provisions detailed below and the amount of the contract shall accordingly be varied, subject to the condition that that such compensation for escalation in prices and wages shall be available only for the work done during the stipulated period of the contract including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2. However, for the work done during the justified period extended as above, the compensation as detailed below will be limited to prices/wages prevailing at the time of updated stipulated date of completion considering the effect
What is the formula provided for Price variation or Escalation? | The provided text mentions a formula in Clause 10CA of the General Conditions of Contract for price variation, but the formula itself is not included in this excerpt. The text describes how price increases/decreases for certain materials (cement, steel, etc.) will be determined using price indices from the Economic Advisor to the Government of India, but the specific calculation formula is not given. | Page 72 | prevailing at the time of updated stipulated date of completion considering the effect of extra work (extra time to be calculated on pro-rata basis only as cost of extra work x stipulated period/tendered cost). The increase/decrease in prices of cement, steel reinforcement, structural steel and POL shall be determined by the Price indices Economic Advisor to Government of India, Ministry of Commerce and Industry. For other items provided in the Special Conditions of Contract, this shall be determined by the All India Wholesale Price Indices of materials as published by Economic Advisor to Government of India, Ministry of Commerce and Industry. Base price for cement, steel reinforcement, structural steel and POL shall be as issued by the state / Central Govt. from time to time. In case, price index of a particular material is not issued by Ministry of Commerce and Industry, then the price index of nearest similar material as indicated in Special Conditions of Contract shall | Page 72 | then the price index of nearest similar material as indicated in Special Conditions of Contract shall be followed. The amount of the contract shall accordingly be varied for all such materials and will be worked out as per the formula given Clause 10CA of General Conditions of Contract. CLAUSE 10CC : PAYMENT DUE TO INCREASE/DECREASE IN PRICES/WAGES (EXCLUDING MATERALS COVERED UNDER CLAUSE 10 CA) AFTER RECEIPT OF TENDER FOR WORKS Page 72 of 324 | Page 74 | and labours, etc. 12.3.1 The increase/decrease in the rates due to deviations/variations shall be decided based on the following criteria:- o) Pricing of deviations a) If the item of work as stipulated in the schedule of quantity/scope of work deviates on plus side, then the rate for the deviated quantity shall be paid at the agreement rate upto the deviation limit as specified in Special Condiiotns of Contract with the same terms & conditions of the contract. Beyond deviation limit as specified in the Special Condiiotns of Contract, rate shall be payable on market rates to be determined based on the relevant documents and prevailing market rates, as per Para (ii) below Page 74 of 324
Change of Scope | Based on the provided text, if the scope of work changes, the contractor will carry out the changes on the same terms and conditions, except for the cost and time, which will be determined based on sub-clauses. The time for completion will be extended proportionally to the additional cost of the changes, plus an additional 25% of that time, or a further reasonable time as determined by the Engineer-in-Charge. However, changes resulting from contractor default will not result in contract price or schedule adjustments. If the Engineer-in-charge decides to reduce the scope of work, the contractor will have no claim for compensation. | Page 74 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 form part of the contract as if originally provided therein and any change in the scope of work as defined in the contract, which the contractor may be directed to do in the manner specified above as part of the works, shall be carried out by the contractor on the same terms and conditions in all respects, except for increase/ decrease in the cost and additional time due to change of scope, to be determined based on the sub-clauses hereunder : m) The time for completion of the works shall, in the event of any deviations resulting in additional cost over the tendered value sum being ordered, be extended, if requested by the contractor, as follows: (i) In the proportion which the additional cost of the altered, additional or substituted works, bears the original tendered value plus (ii) 25% of the time calculated in (i) above or such further additional time as may be considered reasonable by the Engineer-in-Charge. | Page 75 | of Engineer-in-charge, save except to meet any work of emergent nature. iii) Notwithstanding anything to the contrary in this clause 12, any change arising from default of the contractor in the performance of his obligations under this agreement shall not be deemed to be deviations/variations, and shall not result in any adjustment of the contract price or the project completion schedule. CLAUSE 13: FORECLOSURE OF CONTRACT DUE TO ABANDONMENT OR REDUCTION IN SCOPE OF WORK If at any time after acceptance of the tender, Engineer-in-charge shall decide to abandon or reduce the scope of the works for any reason whatsoever and hence not require the whole or any part of the works to be carried out, the Engineer-in-Charge shall give notice in writing to that effect to the contractor and the contractor shall act accordingly in the matter. The contractor shall have no claim to any payment of compensation or otherwise whatsoever, on account of any profit or advantage | Page 76 | that against any payments due to the contractor on this account or otherwise, the Engineer-in- Charge shall be entitled to recover or be credited with any outstanding balances due from the contractor for advance paid in respect of any tool, plants and materials and any other sums which at the date of termination were recoverable by the WAPCOS from the contractor under the terms of the contract. In the event of action being taken under Clause 13 to reduce the scope of work, the contractor may furnish fresh Performance Guarantee on the same conditions, in the same manner and at the same rate for the balance tendered amount and initially valid up to the extended date of completion or stipulated date of completion if no extension has been granted plus minimum 180 days beyond that. Wherever such a fresh Performance Guarantee is furnished by the contractor the Engineer- in- Charge may return the previous Performance Guarantee CLAUSE 14 : Pre-Construction Activities
What is the defination of change of scope? | Based on the provided text, a change of scope refers to any alteration in the work defined in the contract that the contractor may be directed to perform. This includes additions, alterations, or substitutions to the original work. | Page 74 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 form part of the contract as if originally provided therein and any change in the scope of work as defined in the contract, which the contractor may be directed to do in the manner specified above as part of the works, shall be carried out by the contractor on the same terms and conditions in all respects, except for increase/ decrease in the cost and additional time due to change of scope, to be determined based on the sub-clauses hereunder : m) The time for completion of the works shall, in the event of any deviations resulting in additional cost over the tendered value sum being ordered, be extended, if requested by the contractor, as follows: (i) In the proportion which the additional cost of the altered, additional or substituted works, bears the original tendered value plus (ii) 25% of the time calculated in (i) above or such further additional time as may be considered reasonable by the Engineer-in-Charge. | Page 75 | of Engineer-in-charge, save except to meet any work of emergent nature. iii) Notwithstanding anything to the contrary in this clause 12, any change arising from default of the contractor in the performance of his obligations under this agreement shall not be deemed to be deviations/variations, and shall not result in any adjustment of the contract price or the project completion schedule. CLAUSE 13: FORECLOSURE OF CONTRACT DUE TO ABANDONMENT OR REDUCTION IN SCOPE OF WORK If at any time after acceptance of the tender, Engineer-in-charge shall decide to abandon or reduce the scope of the works for any reason whatsoever and hence not require the whole or any part of the works to be carried out, the Engineer-in-Charge shall give notice in writing to that effect to the contractor and the contractor shall act accordingly in the matter. The contractor shall have no claim to any payment of compensation or otherwise whatsoever, on account of any profit or advantage | Page 76 | necessary so as not to cause any damage or injury to the work already done or endanger the safety thereof for any of the following reasons: (a) on account of any default on the part of the contractor or; (b) for proper execution of the works or part thereof for reasons other than the default of the contractor; or Page 76 of 324
What is the Maximum limit with respect to the Contract Value? | The provided text mentions that if the Employer terminates the contract according to Section 3, or is entitled to terminate it according to Section 3, liquidated damages can be the contract value or the amount equivalent to the Performance Bank Guarantee. There is no other maximum limit on contract value specified in the provided text. | Page 71 | materials covered under Clause 10CA and not being a material supplied from the Engineer- in- Charge’s stores in accordance with Clause 10 thereof) and/or wages of labour increases as a direct result of the coming into force of any fresh law, or statutory rule or order (but not due to any changes of rate in sales tax/VAT, Central/State Excise/Custom Duty) beyond the prices/wages prevailing at the time of the last stipulated date of receipt of tenders including extensions, if any, for the work during contract period including the justified period extended under the provisions of clause 5 of the contract without any action under clause 2, then the amount of the contract shall accordingly be varied and provided further that any such increase shall be limited to the price/wages prevailing at the time of updated stipulated date of completion considering effect of extra work (extra time to be calculated on | Page 190 | payment shall be made only for the quantities of the respective agreement item. For deviation in quantities upto 30% (positive deviation) in quantities beyond permissible 5 % positive side, shall be paid on the quoted rates of the respective item, beyond which market shall be admissible as prevailing during the time of execution. Deviation on minus side from the quantities provided in the contract shall be admissible as per the quoted rates only. v. In case of change in specification of any item of the contract and same being available in DSR 2021 with another item also being available in the DSR-2021, variation in cost (Plus/Minus) shall be made as per difference of cost of the respective items in DSR 2021, increased/ decreased by the quoted % (Plus/ Minus)(as quoted by the bidder for the building/item/work in question) and such increase/decrease shall be applicable only for the actual executed quantities to be measured separately. Page 190 of 324 | Page 44 | the damages equivalent to Earnest Money Deposit/ Bid Security. If the Employer has terminated the contract according to Section 3, or if the Employer is entitled to terminate the contract according to Section 3, the Employer shall be entitled to demand and recover from the contractor liquidated damages of the contract value or the amount equivalent to Performance Bank Guarantee. Section 5 – Previous transgression Bidder declares that no previous transgressions occurred in the last three years with any other Company in any country conforming to the anti-corruption approach or with any Public Sector Enterprise in India that could justify his exclusion from the tender process. Page 44 of 324
What is the provision for Release of Payments in case of change of scope? | Based on the provided text, if the change in scope is up to 0.25% of the accepted tendered amount, nothing extra will be paid to the contractor. If the change exceeds 0.25% of the accepted tendered amount, the text mentions payment of deviations/variations but doesn't detail the specific payment provisions. | Page 76 | that against any payments due to the contractor on this account or otherwise, the Engineer-in- Charge shall be entitled to recover or be credited with any outstanding balances due from the contractor for advance paid in respect of any tool, plants and materials and any other sums which at the date of termination were recoverable by the WAPCOS from the contractor under the terms of the contract. In the event of action being taken under Clause 13 to reduce the scope of work, the contractor may furnish fresh Performance Guarantee on the same conditions, in the same manner and at the same rate for the balance tendered amount and initially valid up to the extended date of completion or stipulated date of completion if no extension has been granted plus minimum 180 days beyond that. Wherever such a fresh Performance Guarantee is furnished by the contractor the Engineer- in- Charge may return the previous Performance Guarantee CLAUSE 14 : Pre-Construction Activities | Page 58 | The contractor may, at his option replace the retention amount with an unconditional BG at the following stages: i) After the amount reaches half the value of the limit of retention money; and ii) After the amount reaches the maximum limit of retention money. One-half of the retention money (or BG, which replaced retention money) shall be released on the issue of the taking-over certificate; if the Taking Over Certificates (TOCs) are issued in parts, then in such proportions as the engineer may determine, having regard to the value of such part or section. The other half of the retention money (or BG, which replaced the retention money) shall be released upon expiration of 365 days after the DLP of the works or final payment, whichever is earlier, on certification by the engineer. In the event of different defect liability periods being applicable to different sections or parts, the expiration of defect liability period shall be the latest | Page 74 | bears the original tendered value plus (ii) 25% of the time calculated in (i) above or such further additional time as may be considered reasonable by the Engineer-in-Charge. n) Payment of deviations/variations beyond 0.25% of the accepted tendered amount. In case there is any change in scope as defined in the contract, the contractor shall carry out the changes as per direction of Engineer in Charge and nothing extra shall be payable to the contractor on account of same if the additional cost of such work is up to 0.25% (zero point two five percent) of the accepted tendered amount and worked out as per sub-clause 12.3 below. Variations/deviations upto 0.25% (zero point two five percent) of the accepted tendered amount shall be deducted from overall variations/ deviations for making payment. 12.3 DETERMINATION OF RATES In the event, there is any deviations/variations in work as defined in the contract, the
what is the Provision for amendment in Performance Security in case of change of scope? | If the scope of work is reduced (Clause 13), the contractor may provide a new performance guarantee for the remaining amount. This new guarantee will have the same conditions, manner, and rate as the original, valid until the extended completion date (or original completion date plus 180 days if no extension is granted). The original performance guarantee will then be returned. | Page 119 | the reason for delays in procuring the Performance Security to the satisfaction of the Competent Authority. d) Failure of the successful Bidder to comply with the requirements of performance security shall constitute sufficient grounds for cancellation of the award. e) The Performance Security shall be valid till recording successful Completion of Defect Liability Period . The performance guarantee shall be returned to the Contractor without any interest after completion of Defect Liability Period. Clause 1A Security Deposit Applicable 5% of Tendered Value Release of security Deposit After 1 (one) year of Successful Completion of Defect Liability period without any interest. Page 119 of 324 | Page 76 | that against any payments due to the contractor on this account or otherwise, the Engineer-in- Charge shall be entitled to recover or be credited with any outstanding balances due from the contractor for advance paid in respect of any tool, plants and materials and any other sums which at the date of termination were recoverable by the WAPCOS from the contractor under the terms of the contract. In the event of action being taken under Clause 13 to reduce the scope of work, the contractor may furnish fresh Performance Guarantee on the same conditions, in the same manner and at the same rate for the balance tendered amount and initially valid up to the extended date of completion or stipulated date of completion if no extension has been granted plus minimum 180 days beyond that. Wherever such a fresh Performance Guarantee is furnished by the contractor the Engineer- in- Charge may return the previous Performance Guarantee CLAUSE 14 : Pre-Construction Activities | Page 58 | TENDER NO: WAP/CMU-III/2024-25/SMFPL/Agartala/09 performance guarantee and the Bank is unable to make payment against the said fixed deposit receipt, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the Government to make good the deficit. ii. The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 1 year claim period beyond the date of completion of all contractual obligations of the contractor, including Defect Liability Period (DLP). In case the time for completion of work gets enlarged, the contractor shall get the validity of Performance Security extended to cover such enlarged time. The performance Security shall be refunded to the contractor without interest, after he duly performs and completes all obligations under the contract not later than 365 days of completion of the Defect Liability Period.